Contract Data Requirements List (CDRL)
Program: FT3 Production Follow-On
Date: 24 April 2026
Version: 1
Date of Determination: (Contract Award Date unless otherwise specified on the CDRL)

1. Introduction 
This document was developed in accordance with DOD MIL-STD 31000C and DODM 5010.12 Acquisition and Management of Contractor-Prepared Data. This represents the general requirements for the Technical Data Package (TDP) for this program. 
The purpose of this Attachment, Technical Data Package, is to define the data deliverables due for this program, including the instructions for their development, and delivery. All specific delivery instructions are specified on the CDRL forms or its digital (word, excel, pdf) equivalent. 
2. General Guidelines
The CDRL form, Department of Defense (DD) Form 1423, specifies the data required to be delivered to the Government, as well as the frequency and approval requirements. The Data Item Descriptions (DIDs), listed on the CDRL form, were selected from the Acquisition Streamlining and Standardization Information System (ASSIST) and provide additional direction for data preparation.

3. Communications
Any correspondence related to requests for data delivery deviations and/or amendments, additions or deletions to the CDRL form shall be addressed to the Procuring Contracting Officer (PCO) with a courtesy copy to the Data Management Officer (DMO) (Air Force Nuclear Weapons Center (AFNWC)/NIMED) and the cognizant Program Manager (PM). Copies of all forms and templates noted in this file are available as requested from PM, DMO, or PCO.

4. Codes used in the DD Form 1423
All CDRLs require Government approval. The directions for submittal and approval of data are indicated in Blocks 7, 8, 9, 10, 11, 12, 13, 14, 15, and 16 of the DD Form 1423. Usually, the direction is in the form of a code (explained below). The following abbreviations/codes are common usage within AFNWC.

4.1 Block 7, DD Form 250 Requirements
Block 7 of the CDRL form indicates whether Procurement Quality Assurance (PQA) inspections and acceptance of deliverable data by DD Form 250 is required. “Draft” copies submitted for advance approval and “Preliminary Draft” copies submitted are exempt from the DD Form 250 requirements. Information copies of DD Form 250 to accompany each letter of transmittal for this category of data.

	Code
	Inspection
	Acceptance

	SS
	Source (DD Form 250 or equivalent document)
	Source (DD Form 250 or equivalent document)

	DD
	Destination (DD Form 250 or equivalent document)
	Destination (DD Form 250 or equivalent document)

	SD
	Source (DD Form 250 or equivalent document)
	Destination (DD Form 250 or equivalent document)

	DS
	Destination (DD Form 250 or equivalent document) 
	Source (DD Form 250 or equivalent document)

	LT
	Letter of Transmittal only
	

	NO
	No inspection or acceptance required
	



4.2 Block 8, Approval Code (for PRE-Approval items)
When items of critical data requiring specific advanced approval or draft is required before distribution of final data item should be identified as (code “A”), the approval authority (ORG) for that 1423 is designated in Block 14. When document pre-approval or draft is not required (code “N/A”). When the data item requires submission of a draft document prior to publication of a final document, block 16 of the DD Form 1423 shall show the length of time required for Government approval and/or disapproval and subsequent turn-around time for the contractor to resubmit the data after Government approval and/or disapproval has been issued.

	Code
	Description

	A
	PRE-Approval Required prior to Final Submission

	N/A
	PRE-Approval prior to Final Submission Not Required



4.3 Block 10, Frequency of Submittals
	Code
	Description

	ANNLY
	Annually

	ASGEN
	As generated

	ASREQ or ASREQD
	As required*

	BI-MO
	Each 2 months

	BI-WE
	Each 2 weeks

	DAILY
	Daily

	DFDEL
	Deferred delivery

	EOQ
	End of Quarter

	MTHLY
	Monthly

	ONE/P
	One-time preliminary draft

	ONE/R
	One time and revisions

	OTIME
	One time

	QRTLY
	Quarterly

	R/ASR
	Revisions as required

	SEMIA
	Each 6 months

	WEKLY
	Weekly

	XTIME
	Multiple separate submittals (i.e., 2Time, 3Time)

	
	


* When ASREQD is used in Blocks 10, 11, 12 or 13 an explanation of the requirements must be entered in Block 16.

4.4 Block 11, 12 and 13, Dates of As of, Initial and Subsequent Submissions

	Code
	Description

	ASGEN
	As generated

	ASREQ
or
ASREQD
	As required*

	CDR
	Critical Design Review

	CD
	Calendar Day(s)

	DFDEL
	Deferred delivery

	EOC
	End of contract

	EOM
	End of month

	FQT
	Formal Qualification Test

	FCA
	Functional Configuration Audit

	PCA
	Physical Configuration Audit

	PDR
	Preliminary Design Review

	TRR
	Test Readiness Review

	
	


* When ASREQD is used in Blocks 10, 11, 12 or 13 an explanation of the requirements must be entered in Block 16.

Indicate SEE BLK 16 if submission requirements are listed in Block 16.

5. Supplemental Data Preparation Instructions:

5.1 Data Item Description (DID) Version
The most current version of the DID at the time of the award of the contract or Task Order, whichever date is most current, specified in Block 4, is to be used when submitting data. The most current version can be found at http://quicksearch.dla.mil/. 
5.2 DID Tailoring
The DID is a specification for the preparation of data. A DID may only be tailored down, never added to. DID tailoring is reflected in Block 16 of the CDRL form. “T” entered after the DID number in Block 4, means that the DID has been tailored. Block 4 tailoring is made to either relax preparation instructions or to tailor the DID to be in consonance with the source document tailoring contained in the Statement of Work (SOW), Performance Work Statement (PWS) or Contractor Statement of Work (CSOW).

5.3 Scientific and Technical Information (STINFO) Distribution Statement Markings
The designation in Block 9 of the CDRL form indicates that one of the following six (6) authorized distribution statements from Department of Defense Instruction (DoDI) 5230.24 and Department of the Air Force Instruction (DAFI) 61-201 shall be annotated on that technical data. Distribution statements will be selected to denote the audience for which the data is intended.  A distribution statement marking is distinct from and in addition to a security classification marking assigned in accordance with (IAW) DoDM5200.01V2_AFMAN16-1404V2 Information Security Program: Marking of Classified Information.  Should Block 9 of the CDRL form and the DID be in conflict, Block 9 of the CDRL form shall take precedence. The following distribution statements are authorized for use in marking of all documents:

	Distribution Statement A: 
Approved for public release.  Distribution is unlimited.
	Distribution Statement B: 
Distribution authorized to U.S. Government Agencies (category), (date of determination). Other requests for this document must be referred to MMIII SPO (AFNWC/NIM), 6014 Dogwood Ave, Hill AFB UT 84056

	Distribution Statement C: 
Distribution authorized to U.S. Government Agencies and their contractors (category), (date of determination). Other requests for this document must be referred to MMIII SPO (AFNWC/NIM), 6014 Dogwood Ave, Hill AFB UT 84056.
	Distribution Statement D: 
Distribution authorized to Department of Defense and U.S. DoD contractors only (category), (date of determination). Other requests must be referred to MMIII SPO (AFNWC/NIM), 6014 Dogwood Ave, Hill AFB UT 84056.

	Distribution Statement E: 
Distribution authorized to DoD Components only (category), (date determination). Other requests must be referred to MMIII SPO (AFNWC/NIM), 6014 Dogwood Ave, Hill AFB UT 84056.
	Distribution Statement F: 
Further dissemination only as directed by MMIII SPO (AFNWC/NIM), 6014 Dogwood Ave, Hill AFB UT 84056 (date of determination) or higher DOD authority.



5.4 Other Notices
All technical documents marked with Distribution Statements B, C, D, E, or F will also be marked with the following notices: 

Export Control Warning Statement:   
This document contains technical data whose export is restricted by the Arms Export Control Act (Section 2751 of Title 22, United States Code) or the Export Control Reform Act of 2018 (Chapter 58 Sections 4801-4852 of Title 50, United States Code). Violations of these export laws are subject to severe criminal penalties. Disseminate in accordance with provisions of DoD Directive 5230.25 and DoD Instruction 2040.02.

When the data is export controlled, include Export Control as one of the reasons IAW DoDI 5230.24 Section 3. Paragraph 3.4.i.

DoDD 5230.25 is available online at https://www.esd.whs.mil/DD/. 

NOTE: The CDO Program Manager (PM) may remove the “Export Control Warning” if “critical technology” is not a reason annotated in the distribution statement and if the CDO PM can verify the technical report/document is not export control.

Note – When distributing export-controlled data, include the “Notice to Accompany…” IAW DoDD 5230.25 Enclosure 5, by paper copy or read-me-file. 

Destruction Notice: 
(destruction notices are now optional on Scientific/Technical information documents.)
Documents designated as Distribution B, C, D, E, or F shall be marked with one of the following statements:  

For classified documents:
DESTRUCTION NOTICE:  Follow the procedures in National Industrial Security Program Operating Manual (NISPOM) Title 32 § 117.15(g) and Title 32 § 2001.47, DoDM5200.01V3_DAFMAN16-1404V3 Information Security Program: Protection of Classified Information, Enclosure 3, Paragraph 17.

For unclassified, limited documents: (destruction notices are now optional on Scientific/Technical information documents.
DESTRUCTION NOTICE:  Record and non-record copies of CUI documents will be disposed of IAW Chapter 33 of Title 44, U.S.C. and the DoD Components’ records management directives. When destroying CUI, including in electronic form, agencies must do so in a manner making it unreadable, indecipherable, and irrecoverable.

Controlled Unclassified Information (CUI) Markings 
IAW DoDI5200.48_DAFI16-1403, Controlled Unclassified Information, mark all applicable documents with the appropriate CUI markings and CUI designation indicator block. Place the CUI designation indicator block at the bottom-right side of the first page or cover page when using the Limited Dissemination Control (LDC) marking and if using a distribution statement place CUI designation indicator block above the distribution statement Note - CUI marking requirements do not affect STINFO requirements, All CUI documents determined to warrant the use of a distribution statement must contain Controlled Technical Information (CTI).

5.5 Pricing CDRL Items Separately
If blocks 17 and 18 of the DD form 1423 documents are marked as "N/A" and "NSP" respectively, then the Government does not want to separately group or price CDRL items. If blocks 17 and 18 are left blank, the Government intends to seek separate pricing for the development costs of each CDRL. This pricing is for development costs of the data items and is considered separate from data rights costs.

6. Supplemental Data Delivery Instructions:



6.1 Due Dates
Due dates for delivery of data are to be construed as receipt at destination. Due dates are based on calendar days unless otherwise noted.  If due date falls on a non-business day, i.e. weekend or holiday, due date is pushed to the next business day.

6.2 Late Delivery
Delivery of data is considered late if it does not arrive at its destination by 1530 hours (3:30 PM) Mountain Time on the date specified in Blocks 12, 13, or 16 of the CDRL. 

6.3 Submittal Procedures:

6.3.1 CDRL Submittal Procedure
For the purposes of data submittal, unclassified CDRLs are submitted to the government via TopVue https://icbm.topvue.com/topvue-icbm/.  For access to CDRLvue, the contractor must obtain and maintain T-1 eligibility, National Agency Check with Inquiries (NACI). 
THIS IS FOR UNCLASSIFIED CDRL SUBMITTALS ONLY.  
(See below for Classified CDRL submittals (6.3.2))  
Each data submittal shall be accompanied by a CDA form (please request current version from ORG1). If for any reason a CDA form is not available, a cover letter shall contain the following information: 

1. Contract number
2. CDRL sequence number (e.g., A001)
3. Exact title and subtitle (if applicable) of the document being transmitted
4. Line item or CLIN number
5. Modification Number or Order Number
6. Document date, number, and revision information (if applicable)
7. Data delivery method and date of delivery
8. Whether the document is a draft or final submittal
9. For approval data: State “For Approval”
10. If the document is a re-submittal, reference the Government letter CDA requesting re-submittal or disapproval of previous submittal
11. For periodic reports: The report period that the document covers
12. Distribution: Information disclosing the total contractual distribution being made per Block 14 or Block 16 of the CDRL Form

6.3.2 Classified CDRL Submittal Procedure 
If any deliverables contain classified information, contractor must obtain and maintain T-3 eligibility, National Agency Check with Law and Credit (NACLC).  Classified CDRLs and classified documentation are submitted IAW this instruction and are never to be emailed.*  Classified CDRLs or portions of a CDRL, as applicable, shall be forwarded IAW Appendix B of the DD254 and 32 CFR Part 117, National Industrial Security Program Operating Manual (NISPOM).  For Classified Disks send two (2) copies.

Outer Envelope:
Address
ATTN: AFNWC/NIMS MMIII Security Office

Inner Envelope:
Address
ATTN: Name of person for whom the document should be delivered

*A letter of delivery shall be submitted to TopVue https://icbm.topvue.com/topvue-icbm/csswb/login , when classified data is delivered via the instructions above.

7. Supplemental Data Review and Approval Process:

7.1 CDRL Approvals 
Government must approve/disposition each data item. In addition, Block 16 of the form may contain additional directions. Types of dispositioning that occur are as follows:

	Written Approval
	“Written Approval” indicates agreement or concurrence with the contractor furnished data only and shall not be construed as changing any of the terms or conditions of the subject contract. The approval authority shall be ORG 1 as outlined in section 9 of this document. Approval shall take the form of concurrence using the CDA form, signed and dated by the representative stated in ORG 1. Data items submitted for approvals are NOT automatically approved without government approval. 

	Approved with 
Comment or 
Disapproved
	The Contractor shall revise data items “Approved with Comments or Disapproved” IAW the specific written comments transmitted with the CDA or PCO/DMO letter and resubmit not later than 30 calendar days (unless otherwise directed) from receipt of the “Approved with Comments or Disapproved”, unless otherwise directed. The resubmitted data will require a new approval cycle as indicated in Block 16 of the DD Form 1423.

	Draft Versions 
of the CDRL
	If a DD Form 1423 directs the Contractor to submit a “draft” version of an approval CDRL in advance of the final version, the draft will be considered an information only submission. However, the PM/DMO still retains the right to disapprove a draft data item that does not comply with the contract requirements. Unless otherwise directed by the PCO, the Contractor shall incorporate the Government’s comments in the final submission and shall not resubmit the draft version of the data item.



7.2 Contractual Document Action (CDA)
After the Government receives a data item submission, a Temporary Data Identification (TDID) number, a unique identifier to that submission, will be assigned by the DMO. The Government’s review of that data item will result in a coordinated CDA form, or PCO letter, indicating the data item’s approval or disapproval. Should the Government have comments on the data item, the CDA will include either comments on the CDA form itself or a Comment Resolution Matrix (CRM). Comments will be provided to the submitter IAW the format and timeline noted in block 16. Comments will be assigned one of the following codes:

	COMMENT CODE
	CODE DESCRIPTION

	C
	Critical
	Comments of a very serious nature that will preclude final approval and publication of the document. You are willing to elevate the comment or issue to senior organization leadership (e.g., General Officer) and recommend they non-concur. These are the "show-stoppers". Convincing rationale for critical comments must be provided. The individual making the comment and the document writer will reconcile the comment.

	S
	Substantive
	Comments of a less serious nature that have noticeable impact on the document’s quality or content. The document appears to be incorrect, misleading, confusing, or inconsistent with other sections.

	A
	Administrative
	Comments that address minor items such as typographical, format and/or grammatical errors.



7.3 Information Only CDRLs 
When an “A” is not indicated in Block 8 of the DD Form 1423, the PM/DMO still retains the right to disapprove any data that does not comply with contract requirements. The Contractor shall revise the disapproved data IAW with the specific written comments transmitted with the CDA form or PCO letter and resubmit not later than 30 calendar days, unless otherwise directed, from receipt of the disapproval. The resubmitted data will require a new approval cycle as indicated in Block 8 of the DD Form 1423.

8. Data Accession List (DAL)
During performance of the contract, requests from the PCO for data ordered from the Data Accession List (DAL) (with the application of the current version, for DID DI-MGMT-81453) shall be provided at no increase in contract price. Requests for quantities greater than two each per document shall be honored upon receipt of PCO direction and with Contractor concurrence that such request can be filled at no increase in contract price.

9. Organizational Cross Reference List
The following Organizational Cross Reference List shall be used in conjunction with the CDRLs to determine actual addressees for distribution of data. The ORG number will be entered in lieu of an address on the CDRL and will be a part of the CDRL package. Changes to the list will be identified by an asterisk next to the ORG number and a revision date to the list.  Any changes to the Attention/To or Contract Info list will not require a contract mod.


	ORG#/ Name
	Address
	Attention/To
	Contact Info

	ORG1/AFNWC/NIM
	
Hill AFB UT  84056
	Program PM
	PM’s email

	ORG2/AFNWC/NIM
	
Hill AFB UT  84056
	Program Engineer
	Program Engineer’s email

	ORG3/AFNWC/NIM
	
Hill AFB UT  84056
	Alt Program Manager
	Alt PM’s email

	ORG4/AFNWC/NIMED
	N/A
	
	

	ORG5/AFNWC/NIMED
	N/A
	
	

	ORG6/AFNWC/NIMED
	N/A
	
	

	ORG7/AFNWC/NIML
	6014 Dogwood Ave Bldg 1258
Hill AFB UT  84056
	IUID/Parts Engineering
	afnwc.nies.partsengineering@us.af.mil 

	ORG8/AFNWC/NIME
	N/A
	
	

	ORG9/AFNWC/NIMES
	N/A
	
	

	ORG10/AFNWC/NIMS
	N/A
	
	

	ORG11/AFNWC/NIMES
	N/A
	
	

	ORG12/AFNWC/NIMES
	6054 Dogwood Ave Bldg 1255
Hill AFB UT  84056
	Corrosion
	afnwc.niev.corrosiongroup@us.af.mil 

	ORG13/AFNWC/NIMES
	N/A
	
	

	ORG14/AFNWC/NIML
	N/A
	
	

	ORG15/AFNWC/NIME
	N/A
	
	

	ORG16/AFNWC/NIME
	N/A
	
	

	ORG17/AFNWC/NIMES
	N/A
	
	

	ORG18/AFNWC/NIMET
	N/A
	
	

	ORG19/AFNWC/NIMES
	N/A
	
	

	ORG20/AFNWC/NIME
	N/A
	
	

	ORG21/AFNWC/NIMET
	6054 Dogwood Ave Bldg 1255
Hill AFB UT  84056
	TE (Alt LTDO)
	AFNWC.NIMET.TestandEvaluation@us.af.mil


	ORG22/AFNWC/NIML
	6014 Dogwood Ave, Bldg 1258
Hill AFB, UT 84056
	Program Protection
	ANFWC.NIML.PPT@us.af.mil 

	ORG23/AFNWC/NMASF
	N/A
	
	

	ORG24/AFGSC/A3TT
	N/A
	
	

	ORG25/AFNWC/NMLA	
	N/A
	
	

	ORG26/406 SCMS/GULAB
	N/A
	
	

	ORG27/406 SCMS/GULAA
	N/A
	
	

	ORG28/419 SCMS/GUBA
	N/A
	
	

	ORG29/75 ABW/SE
	N/A
	
	

	ORG30/DCMA/ACO
	N/A
	
	

	ORG31/AFNWC/NIMF
	6008 Wardleigh Rd Bldg 1580
Hill AFB UT  84056
	Cost/Funds
	AFNWC.MMIII.Cost@us.af.mil

	ORG32/AFNWC/PZ
	6008 Wardleigh Rd Bldg 1580
Hill AFB UT  84056
	Program CO
	Program CO Email

	ORG33/AFNWC/NIMED
	6054 Dogwood Ave Bldg 1255
Hill AFB UT  84056
	Data Management
	afnwc.nies.datamgmtoffice@us.af.mil 

	ORG34/AFNWC/NIMES/SIV
	6054 Dogwood Ave Bldg 1255
Hill AFB UT  84056
	SIV
	afnwc.nie.siv@us.af.mil 

	ORG35/AFNWC/AEDC
	N/A
	
	

	ORG36/AFNWC/NIMS
	N/A
	
	

	ORG37/406 SCMS/GULAA
	N/A
	
	

	ORG38/AFNWC/NIMH
	N/A
	
	

	ORG39/OSD CAPE
	OSD CADE
	Cost/Funds
	https://dcarc.cape.osd.mil













	

	10. CDRL Master Listing Index	Comment by WELLS, TAMARA R CTR USAF AFMC AFNWC/NIMG: Discuss adding in the Production Status Report, DI-MGMT-81255 at 2.1.8
	

	Full 1423’s for CDRL’s applicable to this program are included in section 11 of this document.
	

	CDRL#
	Title
	DID#

	CDRL#
	Title
	DID#

	A002
	Meeting Agenda 
	DI-ADMN-81249C

	A003
	Briefing Material 
	DI-MGMT-81605

	A004
	Meeting Minutes 
	DI-ADMN-81250C

	A008.1
	Work Management Plan - Subcontractor Management Plan
	DI-MGMT-81911/T

	A008.2
	Work Management Plan - Small Business Subcontractor Report
	DI-MGMT-81911/T

	A008.3
	Work Management Plan - Transportation Plan
	DI-MGMT-81911/T

	A009
	Manufacturing Plan 
	DI-MGMT-81889B

	A010
	Contractor's Risk Management Plan 
	DI-MGMT-81808

	A013
	Corrosion Prevention and Control Plan (CPCP) 
	DI-MFFP-81403B

	A015
	Quality Assurance Program Plan (QAPP) 
	DI-QCIC-81794B

	A059.1
	Technical Report - Study/Services - Failure/Anomaly Resolution Report
	DI-MISC-80508B/T

	A064
	Acceptance Test Report (ATR) 
	DI-QCIC-81891

	A142
	Supply Chain Risk Management (SCRM) Plan 
	DI-MGMT-82256A

	A168
	Parts, Materials, and Processes (PM&P) Management Plan 
	DI-STDZ-81993A

	A231
	Cost and Hour Report (Flex File) 
	DI-FNCL-82162

	A235
	Contractor Business Data Report (CBDR) - DD Form 1921-3
	DI-FNCL-81765C

	A237
	Technical Data Report 
	DI-MGMT-82165

	A238
	Quantity Data Report - Contractor Cost Data Reporting (CCDR)
	DI-MGMT-82164




11. DD Form 1423s (full 1423’s)
*1423’s, block A Reference Number: CLIN number to be added at time of award
**1423’s block E Reference Number: Contract and Mod/TO number to be added at time of award
***1423’s block G & I will be signed at time of award
****1423’s Reference Blk G for status of CDRL package.  

Prepared by                                                                                     Approved by 
                                       





CONTRACT DATA REQUIREMENTS LIST
(1 Data Item)

Form Approved
OMB No. 0704-0188

The public reporting burden for this collection of information is estimated to average 110 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Department of Defense, Executive Services and Communications Directorate (0704­0188). Respondents should be aware that notwithstanding any other provision of law, no person shall be subject to any penalty for failing to comply with a collection of information if it does not display a currently valid OMB control number.
Please do not return your form to the above organization. Send completed form to the Government Issuing Contracting Officer for the Contract/PR No. listed in Block E.

A. CONTRACT LINE ITEM NO.


B. EXHIBIT
A

C. CATEGORY
TDP

TM

OTHER
X
[image: ]
[image: ]
[image: ]

D. SYSTEM/ITEM
FT3 Production Follow-On

E. CONTRACT/PR NO.
FA8214-28-C-XXXX

F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A002

2. TITLE OF THE DATA ITEM
Meeting Agenda

3. SUBTITLE


4. AUTHORITY
(Data Acquisition Document No.)
DI-ADMN-81249C

5. CONTRACT REFERENCE
PWS Para 2.1.5

6. REQUIRING OFFICE
AFNWC/NIMG
[image: ]

17. PRICE GROUP


18.
ESTIMATED TOTAL PRICE


7. DD 250 REQ
LT

8. APP CODE
N/A

9.
DIST STATEMENT REQUIRED
D

10. FREQUENCY
As Reqd

12.
DATE OF FIRST SUBMISSION
N/A

11. AS OF DATE
N/A

13.
DATE OF SUBSEQUENT SUBMISSION
N/A

14.
DISTRIBUTION


a. ADDRESSEE

b. COPIES



Draft

Final
Reg
Repro

LM
26-11
ORG 1 (LODO)



ORG 2 (LODO)



ORG 32 (LODO)



ORG 33 (LODO)




































































































































































16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit Meeting Agenda, if applicable, NLT 5 business days 
prior to scheduled meetings or meetings deemed necessary by the Government.  
Government will be allowed 2 business days, after receipt from contractor, to 
review for approval/disapproval/comments.  Contractor shall submit revised 
Meeting Agenda incorporating Government comments, if applicable, NLT 2 
business days after receipt from Government.

BLOCK 14:  
For unclassified deliverables, contractor shall submit Meeting Agenda to 
TopVue https://icbm.topvue.com/topvue-icbm/ as per instructions (see 
paragraph 6.3.1).  
For classified deliverables, contractor shall submit Meeting Agenda via 
instructions (see paragraph 6.3.2), and a letter of delivery to TopVue.

 15. TOTAL
0
0
0

G. PREPARED BY


H. DATE


I. APPROVED BY


J. DATE

DD FORM 1423-1, FEB 2001
PREVIOUS EDITION MAY BE USED.

Page 1 of 1 Pages



CONTRACT DATA REQUIREMENTS LIST
(1 Data Item)

Form Approved
OMB No. 0704-0188

The public reporting burden for this collection of information is estimated to average 110 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Department of Defense, Executive Services and Communications Directorate (0704­0188). Respondents should be aware that notwithstanding any other provision of law, no person shall be subject to any penalty for failing to comply with a collection of information if it does not display a currently valid OMB control number.
Please do not return your form to the above organization. Send completed form to the Government Issuing Contracting Officer for the Contract/PR No. listed in Block E.

A. CONTRACT LINE ITEM NO.


B. EXHIBIT
A

C. CATEGORY
TDP

TM

OTHER
X
[image: ]
[image: ]
[image: ]

D. SYSTEM/ITEM
FT3 Production Follow-On

E. CONTRACT/PR NO.
FA8214-28-C-XXXX

F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A003

2. TITLE OF THE DATA ITEM
Briefing Material

3. SUBTITLE


4. AUTHORITY
(Data Acquisition Document No.)
DI-MGMT-81605

5. CONTRACT REFERENCE
PWS Para 2.1.5

6. REQUIRING OFFICE
AFNWC/NIMG
[image: ]

17. PRICE GROUP


18.
ESTIMATED TOTAL PRICE


7. DD 250 REQ
LT

8. APP CODE
N/A

9.
DIST STATEMENT REQUIRED
D

10. FREQUENCY
As Reqd

12.
DATE OF FIRST SUBMISSION
SEE BLK 16

11. AS OF DATE
N/A

13.
DATE OF SUBSEQUENT SUBMISSION
N/A

14.
DISTRIBUTION


a. ADDRESSEE

b. COPIES



Draft

Final
Reg
Repro

LM
26-11
ORG 1 (LODO)



ORG 2 (LODO)



ORG 32 (LODO)



ORG 33 (LODO)




































































































































































16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit Briefing Materials NLT 5 business days prior to 
each scheduled meeting and/or any other meeting deemed necessary by the 
Government and as requested by the Government. Government will be allowed 2 
business days, after receipt from contractor, to review for comments.  
Contractor shall present corrected Briefing Materials incorporating 
Government comments, if applicable, NLT 2 business days after receipt from 
Government.

BLOCK 14:  
For unclassified deliverables, contractor shall submit Briefing Materials to 
TopVue https://icbm.topvue.com/topvue-icbm/ as per instructions (see 
paragraph 6.3.1).  
For classified deliverables, contractor shall submit Briefing Materials via 
instructions (see paragraph 6.3.2), and a letter of delivery to TopVue.
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The public reporting burden for this collection of information is estimated to average 110 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Department of Defense, Executive Services and Communications Directorate (0704­0188). Respondents should be aware that notwithstanding any other provision of law, no person shall be subject to any penalty for failing to comply with a collection of information if it does not display a currently valid OMB control number.
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D. SYSTEM/ITEM
FT3 Production Follow-On

E. CONTRACT/PR NO.
FA8214-28-C-XXXX

F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A004

2. TITLE OF THE DATA ITEM
Meeting Minutes

3. SUBTITLE


4. AUTHORITY
(Data Acquisition Document No.)
DI-ADMN-81250C

5. CONTRACT REFERENCE
PWS Para 2.1.5

6. REQUIRING OFFICE
AFNWC/NIMG
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit Meeting Minutes NLT 15 business days after meeting 
or event has been held.  Government will be allowed 5 business days, after 
receipt from contractor, to review for approval/disapproval/comments. 
Contractor shall submit revised Meeting Minutes incorporating Government 
comments, if applicable, NLT 5 business days after receipt from Government.

BLOCK 14:  
For unclassified deliverables, contractor shall submit Meeting Minutes to 
TopVue https://icbm.topvue.com/topvue-icbm/ as per instructions (see 
paragraph 6.3.1).  For classified deliverables, contractor shall submit 
Meeting Minutes via instructions (see paragraph 6.3.2), and a letter of 
delivery to TopVue.
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Form Approved
OMB No. 0704-0188

The public reporting burden for this collection of information is estimated to average 110 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Department of Defense, Executive Services and Communications Directorate (0704­0188). Respondents should be aware that notwithstanding any other provision of law, no person shall be subject to any penalty for failing to comply with a collection of information if it does not display a currently valid OMB control number.
Please do not return your form to the above organization. Send completed form to the Government Issuing Contracting Officer for the Contract/PR No. listed in Block E.
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D. SYSTEM/ITEM
FT3 Production Follow-On

E. CONTRACT/PR NO.
FA8214-28-C-XXXX

F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A008.1

2. TITLE OF THE DATA ITEM
Work Management Plan

3. SUBTITLE
Subcontractor Management Plan

4. AUTHORITY
(Data Acquisition Document No.)
DI-MGMT-81911/T

5. CONTRACT REFERENCE
PWS Para 2.1.8.1.1

6. REQUIRING OFFICE
AFNWC/NIMG
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements). 

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit Work Management Plan (Subcontractor Management 
Plan) NLT 30 business days after request from Government. Government will 
be allowed 20 business days, after receipt from contractor, to review for 
approval/disapproval/comments.  Contractor shall submit revised Work 
Management Plan (Subcontractor Management Plan) incorporating Government 
comments, if applicable, NLT 20 business days after receipt from Government.

BLOCK 14:  
For unclassified deliverables, contractor shall submit Work Management Plan 
(Subcontractor Management Plan) to TopVue https:
//icbm.topvue.com/topvue-icbm/ as per instructions (see paragraph 6.3.1).  
For classified deliverables, contractor shall submit Work Management Plan 
(Subcontractor Management Plan) via instructions (see paragraph 6.3.2), and 
a letter of delivery to TopVue.
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The public reporting burden for this collection of information is estimated to average 110 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Department of Defense, Executive Services and Communications Directorate (0704­0188). Respondents should be aware that notwithstanding any other provision of law, no person shall be subject to any penalty for failing to comply with a collection of information if it does not display a currently valid OMB control number.
Please do not return your form to the above organization. Send completed form to the Government Issuing Contracting Officer for the Contract/PR No. listed in Block E.
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D. SYSTEM/ITEM
FT3 Production Follow-On

E. CONTRACT/PR NO.
FA8214-28-C-XXXX

F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A008.2

2. TITLE OF THE DATA ITEM
Work Management Plan

3. SUBTITLE
Small Business Subcontractor Report

4. AUTHORITY
(Data Acquisition Document No.)
DI-MGMT-81911/T

5. CONTRACT REFERENCE
PWS Para 2.1.8.1.2

6. REQUIRING OFFICE
AFNWC/NIMG
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit Work Management Plan (Small Business 
Subcontractor Report) NLT 30 business days after request from 
Government. Government will be allowed 20 business days, after receipt from 
contractor, to review for approval/disapproval/comments.  Contractor shall 
submit revised Work Management Plan (Small Business Subcontractor Report)
incorporating Government comments, if applicable, NLT 20 business days 
after receipt from Government.

BLOCK 14:  
For unclassified deliverables, contractor shall submit Work Management Plan 
(Small Business Subcontractor Report) to TopVue https:
//icbm.topvue.com/topvue-icbm/ as per instructions (see paragraph 6.3.1).  For classified deliverables, contractor shall submit Work Management Plan 
(Small Business Subcontractor Report) via instructions (see paragraph 6.3.2)
, and a letter of delivery to TopVue.
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E. CONTRACT/PR NO.
FA8214-28-C-XXXX

F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A008.3

2. TITLE OF THE DATA ITEM
Work Management Plan

3. SUBTITLE
Transportation Plan

4. AUTHORITY
(Data Acquisition Document No.)
DI-MGMT-81911/T

5. CONTRACT REFERENCE
PWS Para 2.1.7.3

6. REQUIRING OFFICE
AFNWC/NIMG
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit Work Management Plan (Transportation Plan) NLT 
30 business days after request from Government. Government will be allowed 20 
business days, after receipt from contractor, to review for 
approval/disapproval/comments.  Contractor shall submit revised Work 
Management Plan (Transportation Plan) incorporating Government comments, 
if applicable, NLT 20 business days after receipt from Government.

BLOCK 14:  
For unclassified deliverables, contractor shall submit Work Management Plan 
(Transportation Plan) to TopVue https://icbm.topvue.com/topvue-icbm/ as per 
instructions (see paragraph 6.3.1).  For classified deliverables, contractor 
shall submit Work Management Plan (Transportation Plan) via instructions 
(see paragraph 6.3.2), and a letter of delivery to TopVue.
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The public reporting burden for this collection of information is estimated to average 110 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Department of Defense, Executive Services and Communications Directorate (0704­0188). Respondents should be aware that notwithstanding any other provision of law, no person shall be subject to any penalty for failing to comply with a collection of information if it does not display a currently valid OMB control number.
Please do not return your form to the above organization. Send completed form to the Government Issuing Contracting Officer for the Contract/PR No. listed in Block E.
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F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A009

2. TITLE OF THE DATA ITEM
Manufacturing Plan

3. SUBTITLE


4. AUTHORITY
(Data Acquisition Document No.)
DI-MGMT-81889B

5. CONTRACT REFERENCE
PWS Para 2.1.6.1
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AFNWC/NIMG
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit an updated Manufacturing Plan NLT 30 days upon request from the Government.  Government will be allowed 15 business days, after receipt from contractor, to review for approval/disapproval/comments.  Contractor shall submit updated Manufacturing Plan incorporating Government comments, if applicable, NLT 10 days after receipt from Government.

BLOCK 14:  
For unclassified deliverables, contractor shall submit Manufacturing Plan to 
TopVue https://icbm.topvue.com/topvue-icbm/ as per instructions (see 
paragraph 6.3.1).  For classified deliverables, contractor shall submit 
Manufacturing Plan via instructions (see paragraph 6.3.2), and a letter of 
delivery to TopVue.
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The public reporting burden for this collection of information is estimated to average 110 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Department of Defense, Executive Services and Communications Directorate (0704­0188). Respondents should be aware that notwithstanding any other provision of law, no person shall be subject to any penalty for failing to comply with a collection of information if it does not display a currently valid OMB control number.
Please do not return your form to the above organization. Send completed form to the Government Issuing Contracting Officer for the Contract/PR No. listed in Block E.
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E. CONTRACT/PR NO.
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F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A010

2. TITLE OF THE DATA ITEM
Contractor's Risk Management Plan

3. SUBTITLE


4. AUTHORITY
(Data Acquisition Document No.)
DI-MGMT-81808

5. CONTRACT REFERENCE
PWS Para 2.1.8.2.1

6. REQUIRING OFFICE
AFNWC/NIMG
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit an updated Contractor’s Risk Management Plan NLT 30 days upon requested from the Government.  Government will be allowed 15 business days, after receipt from contractor, to review for comment.  Contractor shall submit revised Risk Management Plan incorporating Government comments, if applicable, NLT 15 days after receipt from Government. Contractor shall submit subsequent submittals NLT 10 days after Government request.

BLOCK 14:  
For unclassified deliverables, contractor shall submit Contractor’s Risk 
Management Plan to TopVue https://icbm.topvue.com/topvue-icbm/ as per 
instructions (see paragraph 6.3.1).  For classified deliverables, contractor 
shall submit Contractor’s Risk Management Plan via instructions (see 
paragraph 6.3.2), and a letter of delivery to TopVue.
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The public reporting burden for this collection of information is estimated to average 110 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Department of Defense, Executive Services and Communications Directorate (0704­0188). Respondents should be aware that notwithstanding any other provision of law, no person shall be subject to any penalty for failing to comply with a collection of information if it does not display a currently valid OMB control number.
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E. CONTRACT/PR NO.
FA8214-28-C-XXXX

F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A013

2. TITLE OF THE DATA ITEM
Corrosion Prevention and Control Plan (CPCP)

3. SUBTITLE


4. AUTHORITY
(Data Acquisition Document No.)
DI-MFFP-81403B

5. CONTRACT REFERENCE
PWS Para 2.1.6.3

6. REQUIRING OFFICE
AFNWC/NIMES
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit an updated Corrosion Prevention & Control Plan (CPCP) NLT 30 calendar days upon request from the Government.  Government will be allowed 15 business days, after receipt from contractor, to review for comment.  Contractor shall submit revised CPCP incorporating Government comments, if applicable, NLT 10 days after receipt from Government.

Contractor shall submit a final 
Corrosion Prevention & Control Plan NLT 30 calendar days prior to 
PDR. Thereafter, contractor shall submit the Corrosion Prevention & 
Control Plan NLT 30 calendar days after a required change/modification to 
the plan is identified.

For each Corrosion Prevention & Control Plan submittal, Government will be 
allowed 30 calendar days, after receipt from contractor, to review for 
approval/disapproval/comments.  If comments are returned, Contractor shall 
adjudicate comments with originator or delegate and submit revised Corrosion 
Prevention & Control Plan incorporating Government comments NLT 30 
calendar days after receipt of final comments from Government.

BLOCK 14:  
For unclassified deliverables, contractor shall submit Corrosion Prevention 
& Control Plan to TopVue https://icbm.topvue.com/topvue-icbm/ as per 
instructions (see paragraph 6.3.1).  For classified deliverables, contractor 
shall submit Corrosion Prevention & Control Plan via instructions (see 
paragraph 6.3.2), and a letter of delivery to TopVue.
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The public reporting burden for this collection of information is estimated to average 110 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Department of Defense, Executive Services and Communications Directorate (0704­0188). Respondents should be aware that notwithstanding any other provision of law, no person shall be subject to any penalty for failing to comply with a collection of information if it does not display a currently valid OMB control number.
Please do not return your form to the above organization. Send completed form to the Government Issuing Contracting Officer for the Contract/PR No. listed in Block E.
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F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A015

2. TITLE OF THE DATA ITEM
Quality Assurance Program Plan (QAPP)

3. SUBTITLE


4. AUTHORITY
(Data Acquisition Document No.)
DI-QCIC-81794B

5. CONTRACT REFERENCE
PWS Para 2.1.6.5

6. REQUIRING OFFICE
AFNWC/NIMG
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit an updated Quality Assurance Program Plan NLT 30 
days upon request by the Government. Government will be allowed 15 business days, after receipt from contractor, to review for comment.  Contractor shall submit revised QAPP incorporating Government comments, if applicable, NLT 10 days after receipt from Government.

BLOCK 14:  
For unclassified deliverables, contractor shall submit Quality Assurance 
Program Plan to TopVue https://icbm.topvue.com/topvue-icbm/ as per 
instructions (see paragraph 6.3.1).  For classified deliverables, contractor 
shall submit Quality Assurance Program Plan via instructions (see paragraph 
6.3.2), and a letter of delivery to TopVue.

NOTE:  Quality Assurance Program Plan shall be submitted IAW AS 9100.
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F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A059.1

2. TITLE OF THE DATA ITEM
Technical Report - Study/Services

3. SUBTITLE
Failure/Anomaly Resolution Report

4. AUTHORITY
(Data Acquisition Document No.)
DI-MISC-80508B/T

5. CONTRACT REFERENCE
PWS Paras 2.1.3.9, 2.1.3.10

6. REQUIRING OFFICE
AFNWC/NIMES/SIV
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 4:  
1.   Paragraph 2., add the words “Contractor Format Acceptable” after Format.
2.   Delete paragraphs 2. (a) & (b) in their entirety.

BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit Technical Report – Study/Services 
(Failure/Anomaly Resolution Report) NLT 30 days after completion of 
analysis. Government will be allowed 20 business days, after receipt from 
contractor, to review for approval/disapproval/comment.  Contractor shall 
submit revised Technical Report – Study/Services (Failure/Anomaly 
Resolution Report) incorporating Government comments, if applicable, NLT 
10 days after receipt from Government.

BLOCK 14:  
For unclassified deliverables, contractor shall submit Technical Report – 
Study/Services (Failure/Anomaly Resolution Report) to TopVue
https://icbm.topvue.com/topvue-icbm/ as per instructions (see paragraph 6.3.1).  
For classified deliverables, contractor shall submit Technical Report – 
Study/Services (Failure/Anomaly Resolution Report) via instructions (see 
paragraph 6.3.2), and a letter of delivery to TopVue.

 15. TOTAL
0
0
0

G. PREPARED BY


H. DATE


I. APPROVED BY


J. DATE

DD FORM 1423-1, FEB 2001
PREVIOUS EDITION MAY BE USED.

Page 1 of 1 Pages



CONTRACT DATA REQUIREMENTS LIST
(1 Data Item)

Form Approved
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F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A064

2. TITLE OF THE DATA ITEM
Acceptance Test Report (ATR)

3. SUBTITLE


4. AUTHORITY
(Data Acquisition Document No.)
DI-QCIC-81891

5. CONTRACT REFERENCE
See Block 16

6. REQUIRING OFFICE
AFNWC/NIMET
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
Block 5: PWS Paras 2.1.3.1, 2.1.3.15, 2.1.3.16, 2.1.3.18, 2.1.7.5

BLOCK 9:
Distribution Statement E: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit Acceptance Test Report (ATR), in editable 
WORD format, NLT 30 calendar days after final test event.  Government 
Integrated Test Team (ITT) will be allowed up to 18 days, after receipt 
from contractor, to provide Comment Resolution Matrix (CRM), which allows 
up to 14 days for formal review, and 4 days for consolidation.  The contractor has up to 4 days after CRM receipt from government to provide government ITT with CRM decision (i.e. provide accept/modify/reject response) and updated ATR with accepted CRM comments implemented.  The contractor has 
up to 4 days to conduct a meeting with the government ITT for CRM 
modify/reject resolution.  The contractor has up to 4 days to submit 
adjudicated ATR (i.e. ATR modified to include CRM accepted comments 
and adjudicated modify/reject decision comments) to government for 
signature/approval.  The government has up to 15 business days, after receipt 
from contractor, to approve/reject ATR.
  
NOTE: The ATR shall be submitted IAW 
DODI5000.89_DAFI99-103, ICBMSD HB-99-1103 Test Management, 
and prepared using ICBMSD HB-99-1103 Test Management Attachment 7 
template, please contact AFNWC/NIMET Test and
Evaluation for the latest guidance. The ATR approval is required prior 
to FCA/PCA.

BLOCK 14:  
For unclassified deliverables, contractor shall submit ATR to TopVue, 
https://icbm.topvue.com/topvue-icbm/topvue-icbm/ as per instructions (see 
paragraph 6.3.1).  For classified deliverables, contractor shall submit ATR 
via instructions (see paragraph 6.3.2), and a letter of delivery to TopVue.

 15. TOTAL
0
0
0

G. PREPARED BY


H. DATE


I. APPROVED BY


J. DATE

DD FORM 1423-1, FEB 2001
PREVIOUS EDITION MAY BE USED.

Page 1 of 1 Pages



CONTRACT DATA REQUIREMENTS LIST
(1 Data Item)

Form Approved
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The public reporting burden for this collection of information is estimated to average 110 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Department of Defense, Executive Services and Communications Directorate (0704­0188). Respondents should be aware that notwithstanding any other provision of law, no person shall be subject to any penalty for failing to comply with a collection of information if it does not display a currently valid OMB control number.
Please do not return your form to the above organization. Send completed form to the Government Issuing Contracting Officer for the Contract/PR No. listed in Block E.
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F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A142

2. TITLE OF THE DATA ITEM
Supply Chain Risk Management (SCRM) Process

3. SUBTITLE


4. AUTHORITY
(Data Acquisition Document No.)
DI-MGMT-82147B

5. CONTRACT REFERENCE
PWS Para 2.1.8.2.5

6. REQUIRING OFFICE
AFNWC/NIML
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit the SCRM Process no later than (NLT) 60 
business days after contract award. Government will be allowed 30 business 
days, after receipt from contractor, to review for 
approval/disapproval/comments.  Contractor shall incorporate Government 
comments, if applicable, and submit a revised SCRM Process NLT 10 
business days after receiving comments.

Contractor shall scan the supply chain and identify, assess, plan for, and 
mitigate actual or potential threats, vulnerabilities, and disruptions to the 
program supply chain throughout the lifecycle to ensure mission effectiveness. 
When assessing supply chain risks, Contractor shall consider supply chain 
risk categories identified by the Air Force, including but not limited to 
technology and cybersecurity, economic, transportation and distribution, 
manufacturing and supply, financial, product quality and design, political and regulatory, foreign influence, human capital, compliance, environmental, and infrastructure risks. The Contractor's SCRM Process shall describe 
protection of the supply chain from exploitation due to insertion of 
counterfeits or malware, unauthorized production, tampering, theft, insertion 
of malicious software and hardware, functionality alteration, and other 
elements enabling adversary unauthorized access to data, data alteration, 
communications interruption, or operational disruption. The Contractor shall 
inform and include the Government in mitigations or alterations to the 
program. Contractor shall define the process for reporting incidents and 
inform the Government of incidents impacting the program. In accordance 
with DFARS 252.204-7012 (Safeguarding Covered Defense Information 
and Cyber Incident Reporting), Contractor shall report cyber incidents to 
the Defense Industrial Base Cyber Security Program and to the responsible 
contracting officer, not to exceed 3 days after initial detection. The 
SCRM Process shall address supply chain risks that could jeopardize the 
integrity of products, services, people, and technologies; compromise 
intellectual property; disrupt the flow of product, materiel, information, and finances needed for continued Air Force operations; and drive materiel cost increases to the program. Contractor shall develop and execute processes for identifying supply chain risks as early as possible; persistent and 
comprehensive tracking, monitoring, and re-evaluation of supply chain risks and corresponding mitigation actions; and communicating supply chain risks to 
affected stakeholders and the Government. Contractor shall provide a Supply 
Chain Risk Register for identified actual and potential supply chain risks. 
Contractor's SCRM program and processes shall apply to the prime and their 
suppliers, subcontractors, associated integrators, and vendors, spanning the 
entirety of the supply chain from raw material stage to delivery of a finished product or service. Contractor shall inform and work with counterintelligence agencies, such as the Office of Special Investigations and the Federal Bureau of Investigations, to address foreign intelligence threats, including allowing access to personnel who work on the program for briefings and debriefings.

Contractor shall allow counterintelligence agencies access to personnel and 
facilities for conducting counterintelligence operations and investigations in
See continuation sheet...
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F. CONTRACTOR
Boeing - Defense, Space & Security

16. REMARKS  (Continued)
facilities for conducting counterintelligence operations and investigations in support of the program. Contractor shall deliver and update the listing of all contractor/subcontractors for program-related support personnel who have access to and handling of program information.

Contractor shall conduct a review of the SCRM Process every 24 months from the date of the previously approved 
SCRM Process. Contractor shall notify the Government that a review was conducted via a Memorandum for Record 
(MFR) email within 10 business days of completion. Any necessary changes identified shall be sent to the Government 
for review and approval. Contractor shall submit identified changes to the SCRM Process NLT 10 business days; 
the Government shall review for approval within 10 business days of receipt.

BLOCK 14:  
For unclassified deliverables, contractor shall submit SCRM Process to TopVue https://icbm.topvue.com/topvue-icbm/ 
as per instructions (see paragraph 6.3.1).  For classified deliverables, contractor shall submit SCRM Process via 
instructions (see paragraph 6.3.2), and a letter of delivery to TopVue.
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F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A168

2. TITLE OF THE DATA ITEM
See Block 16

3. SUBTITLE


4. AUTHORITY
(Data Acquisition Document No.)
DI-STDZ-81993A

5. CONTRACT REFERENCE
PWS Para 2.1.4.1

6. REQUIRING OFFICE
AFNWC/NIMG
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
Block 2: Parts, Materials, and Processes (PM&P) Management Plan

BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractor shall submit an updated Parts, Materials, and Processed (PM&P) 
NLT 30 calendar days upon request from the Government.  Government will be allowed 15 business days, after receipt from contractor, to review for comment.  Contractor shall submit revised PM&P incorporating Government comments, if applicable, NLT 10 days after receipt from Government.

BLOCK 14:  
For unclassified deliverables, contractor shall submit PM&P Management 
Plan to TopVue https://icbm.topvue.com/topvue-icbm/ as per instructions (see 
paragraph 6.3.1). For classified deliverables, contractor shall submit 
PM&P Management Plan via instructions (see paragraph 6.3.2), and a letter 
of delivery to TopVue.
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F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A231

2. TITLE OF THE DATA ITEM
Cost and Hour Report (Flex File)

3. SUBTITLE


4. AUTHORITY
(Data Acquisition Document No.)
DI-FNCL-82162

5. CONTRACT REFERENCE
PWS Para 2.1.8.3.3

6. REQUIRING OFFICE
AFNWC/NIMF
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10-13:  
Prepare the Cost and Hour Report (FlexFile) in accordance with 
DI-FNCL-82162 and the OSD CAPE Deputy Director, Cost 
Assessment (DDCA)-approved contract CSDR Plan. The DID, 
DI-FNCL-82162, is available from the Cost Assessment Data 
Enterprise (CADE) website at https://cade.osd.mil/policy/dids. The 
CSDR Plan is included as a contract attachment. Official Approval of the 
deliverables is through OSD CAPE/DCARC. The approvals are shown as 
“Accepted” and “Finalized” in the CADE database.

Contractors shall be required to submit the Cost and Hour Report (FlexFile)
at frequencies specified in the CAPE-approved CSDR plan. The 
Government will be allowed 30 business days, after receipt from contractor, to review for approval/disapproval/comments. Contractor shall submit updated 
Cost and Hour Report(FlexFile), incorporating Government comments, if 
applicable, NLT 30 business days after receipt from Government. The 
contract CSDR plan uses the event field as the driver for the submission of 
the reports, not the "as of date." If the event slips, the contractor must 
notify the Government Program Office that a date change is needed. It is 
the responsibility of the Government Program Office to submit a request for 
change in the event-driven date for reporting through the CADE website 
for CAPE approval before relief is given for the date reflected in the 
CAPE-approved CSDR Plan. 

The FlexFile shall be delivered in either a) MS Excel (.xlsx) or comma 
separated values (.csv) in accordance with the FlexFile & Quantity 
cPet-compatible templates and the DD FORM 2794, or b) JavaScript 
Object Notation (JSON) as described in the FlexFile File Format 
Specification (FFS) and Data Exchange Instructions (DEI) referenced 
in the FlexFile DID Requirements Section 2 and available on the CADE 
website at https://cade.osd.mil. 

All files shall be submitted electronically using the CADE website. Data 
submitters must register through the CADE website and possess a 
DoD-approved ECA digital certificate or DoD-issued CAC to obtain 
a CADE Portal account and be authorized to upload CSDR content. Users 
can obtain access by submitting user information about themselves and their 
organizations to the CADE Portal and requesting a CSDR submitter user 
role. After the registration information has been verified, CAPE shall 
authorize the user account and requested roles. All CADE Portal accounts 
need to be renewed at least annually.

Subcontractor Reporting: Prime contractors shall ensure CSDR requirements 
contained in their prime contracts are flowed down to all subcontractors who 
meet the reporting thresholds specified in the DoDI 5000.73, or as required 
by the cost working integrated product team (CWIPT). This includes 
requiring subcontractors to electronically report directly to CAPE using 
the CSDR Submit-Review System. 

The prime contractor shall be required to work with the CWIPT and all
See continuation sheet...
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16. REMARKS  (Continued)
appropriate subcontractors to prepare separate subcontract CSDR plans for submission to the CAPE for DDCA approval.

The Office of the Secretary of Defense (OSD) Cost Assessment & Program Evaluation (CAPE) may use a CADE 
management support contractor to review the data submitted under this CDRL to ensure contractual requirements are met 
and to facilitate distribution of the data to authorized Government users (hereinafter referred to as "the support 
contractor"). This data may include information that is considered a trade secret, proprietary, business sensitive, or 
otherwise protected pursuant to law or regulation (hereinafter referred to as “protected information”). Execution of 
this contract by the contractor is considered consent to CAPE's permitting access to any information, irrespective of 
restrictive markings or the nature of the information submitted, by its CADE management support contractor for the 
limited purpose of executing its CADE management support contract responsibilities.

BLOCK 14:  Contractor shall submit a letter of delivery of Cost and Hour Report to TopVue https:
//icbm.topvue.com/topvue-icbm/ and deliver electronically the report to CADE’s website https://cade.osd.mil/.
DD FORM 1423-1, FEB 2001
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F. CONTRACTOR
Boeing - Defense, Space & Security

1. DATA ITEM NO.
A235

2. TITLE OF THE DATA ITEM
Contractor Business Data Report (CBDR)

3. SUBTITLE
DD Form 1921-3

4. AUTHORITY
(Data Acquisition Document No.)
DI-FNCL-81765C

5. CONTRACT REFERENCE
PWS Para 2.1.8.3.3

6. REQUIRING OFFICE
AFNWC/NIMF
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Contractors shall be required to submit 1921-3 Contractor Business Data 
Report on an annual basis within 60 days subsequent to the end of the 
contractor's fiscal year for the life of the contract in accordance with 
DI-FNCL-81765C. The Government will be allowed 30 business days, after 
receipt from contractor, to review for approval/disapproval/comments. 
Contractor shall submit updated Contractor Business Data Report, 
incorporating Government comments, if applicable, NLT 30 business days after 
receipt from Government. Only one report is required to be completed and 
submitted by each FPR (Forward Pricing Rate) unit (e.g., plant, site, 
business unit) per year, independent of the number of contracts within the 
FPR unit which contain this CDRL item. The Contractor Business Data 
Report is to be prepared by and for the business entity (e.g., plant, site, or business unit) responsible for submitting the Forward Pricing Rate 
Proposal (FPRP) representing the basis for Forward Pricing Rate 
Agreement (FPRA) negotiations with the government. In the absence of a 
FPR requirement, the term “FPR unit” should be interpreted for reporting 
purposes as “business unit” as defined in the FAR.  

All 1921-3 reports shall be submitted electronically using the 1921-3 & FPR 
Submit-Review System. The required form and file type for each 1921-3 
report is specified in its Data Item Description (DID) located here: 
https://CADE.OSD.MIL/Policy/DIDs. Data submitters must 
register through the CADE website (https://cade.osd.mil) and possess a 
DoD-approved ECA digital certificate or a DoD-issued CAC to 
obtain a CADE Portal account and be authorized to upload CSDR 
content. Users can obtain access by submitting user information about 
themselves and their organizations to the CADE Portal and requesting a 
CSDR submitter user role. After the registration information has been 
verified, CAPE shall authorize the user account and requested role. 
All CADE Portal accounts need to be renewed at least annually. Official 
Approval of the deliverables is through OSD CAPE/DCARC. The 
approvals are shown as “Accepted” and “Finalized” in the CADE database.

CSDR requirements contained in their prime contracts to all subcontractors 
who meet the reporting thresholds specified in the DoDI 5000.73, or as 
required by the CWIPT. This includes requiring subcontractors to 
electronically report directly to CAPE using the CSDR Submit-Review System.

The Office of the Secretary of Defense (OSD) Cost Assessment & 
Program Evaluation (CAPE) may use a CADE management support 
contractor to review the data submitted under this CDRL to ensure 
contractual requirements are met and to facilitate distribution of the data to authorized Government users (hereinafter referred to as "the support 
contractor").  This data may include information that is considered a trade 
secret, proprietary, business sensitive, or otherwise protected pursuant to law or regulation (hereinafter referred to as “protected information”).  Execution of this contract by the contractor is considered consent to CAPE's 
permitting access to any information, irrespective of restrictive markings or 
the nature of the information submitted, by its CADE management support
See continuation sheet...
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16. REMARKS  (Continued)
contractor for the limited purpose of executing its CADE management support contract responsibilities.

BLOCK 14:  Contractor shall submit a letter of delivery of Contractor Business Data Report (DD Form 1921-3) to TopVue
https://icbm.topvue.com/topvue-icbm/ and deliver electronically the report to CADE’s website https://cade.osd.mil/.
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The public reporting burden for this collection of information is estimated to average 110 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Department of Defense, Executive Services and Communications Directorate (0704­0188). Respondents should be aware that notwithstanding any other provision of law, no person shall be subject to any penalty for failing to comply with a collection of information if it does not display a currently valid OMB control number.
Please do not return your form to the above organization. Send completed form to the Government Issuing Contracting Officer for the Contract/PR No. listed in Block E.
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

BLOCKS 10, 11, 12 & 13:  
Prepare the Technical Data Report (TDR) in accordance with 
DI-MGMT-82165 (or the most recently approved version) and the OSD 
Deputy Director, Cost Assessment (DDCA)-approved contract 
CSDR Plan. The DID, DI-MGMT-82165, is available from the 
Cost Assessment Data Enterprise (CADE) website at https:
//CADE.OSD.MIL/Policy/DIDs. The CSDR Plan is included as a 
contract attachment. Official Approval of the deliverables is through 
OSD CAPE/DCARC. The approvals are shown as “Accepted” and 
“Finalized” in the CADE database.
 
Contractors shall be required to submit Technical Data Reports at 
frequencies specified in the OSD DDCA-approved CSDR plan and in the 
contract. The "As of Dates" and "Due Dates" are notional and subject to 
change. The Government will be allowed 30 business days, after receipt from 
contractor, to review for approval/disapproval/comments. Contractor shall 
submit updated Technical Data Report (TDR), incorporating Government 
comments, if applicable, NLT 30 business days after receipt from Government.
The CSDR plan uses the submission event names as the driving mechanism for 
the submittal of the cost reports, not the "as of date." In the event of a 
programmatic schedule slip, the Reporting Entity shall notify the 
Government Program Office that a date change is needed. It is the 
responsibility of the Government Program Office to submit a date change 
request with supporting documentation in the CADE system for the 
event-driven submission for CAPE approval. CAPE will not issue an 
updated OSD DDCA-approved contract CSDR plan for revisions based 
solely on date changes. 

Any alternative CDRL identified through the CWIPT process that meets 
the requirements for technical parameter reporting should be submitted using 
the CADE CSDR Submit-Review System along with the TDR for each 
required submission event. Alternative CDRLs can be uploaded as "Other" 
file types. 

All Technical Data Reports shall be submitted electronically using 
the CADE CSDR Submit-Review System. Only unclassified technical 
data may be uploaded to the CADE Portal. All Technical Data must be 
reviewed by the contractor prior to submission for CADE to ensure that 
aggregation of the technical data does not warrant a higher classification 
level.

The required file format for each Technical Data Report is specified in its 
Data Item Description (DID), unless the DDCA-approved CSDR plan 
specifies another format. Data submitters must register through the CADE 
website (https://cade.osd.mil) and possess a DoD-approved ECA digital 
certificate or a DoD-issued CAC to obtain a CADE Portal account and 
be authorized to upload CSDR content. Users can obtain access by 
submitting user information about themselves and their organizations to the 
CADE Portal and requesting a CSDR submitter user role. After the 
registration information has been verified, CAPE shall authorize the user
See continuation sheet...
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16. REMARKS  (Continued)
account and requested role. All CADE Portal accounts need to be renewed at least annually.

Subcontractor Reporting: Prime contractors are responsible for flowing down CSDR requirements contained in their 
prime contracts to all subcontractors who meet the reporting thresholds specified in the DoDI 5000.73, or as required 
by the CWIPT. This includes requiring subcontractors to electronically report directly to CADE Portal 
using the CSDR Submit-Review System. 

The prime contractor shall be required to work with the CWIPT and all appropriate subcontractors to prepare separate 
subcontract CSDR plans for submission to the DCARC for approval. 

Technical data will be available to support contractors who work for the Office of the Secretary of Defense (OSD) 
or the services. Access to the data is only granted while the contractor is supporting a legitimate Department of 
Defense (DoD) contract, the contractor has a need-to-know, and a Non-Disclosure Agreement (NDA) has been signed 
with the Government organization that the contractor supports. 

The Office of the Secretary of Defense (OSD) Cost Assessment & Program Evaluation (CAPE) may use a CADE 
management support contractor to review the data submitted under this CDRL to ensure contractual requirements are met 
and to facilitate distribution of the data to authorized Government users (hereinafter referred to as "the support 
contractor"). This data may include information that is considered a trade secret, proprietary, business sensitive, or 
otherwise protected pursuant to law or regulation (hereinafter referred to as “protected information”). Execution of 
this contract by the contractor is considered consent to CAPE's permitting access to any information, irrespective of 
restrictive markings or the nature of the information submitted, by its CADE management support contractor for the 
limited purpose of executing its CADE management support contract responsibilities.

BLOCK 14:  Contractor shall submit a letter of delivery of Technical Data Report to TopVue, https:
//icbm.topvue.com/topvue-icbm/. All Technical Data Reports shall be submitted electronically to CADE CSDR 
Submit-Review System at CADE’s website https://cade.osd.mil/. Only unclassified technical data may be uploaded 
to the CADE Portal.  All Technical Data must be reviewed by the contractor prior to submission to submission 
for CADE to ensure that aggregation of the technical data does not warrant a higher classification level.
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Form Approved
OMB No. 0704-0188

The public reporting burden for this collection of information is estimated to average 110 hours per response, including the time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, to the Department of Defense, Executive Services and Communications Directorate (0704­0188). Respondents should be aware that notwithstanding any other provision of law, no person shall be subject to any penalty for failing to comply with a collection of information if it does not display a currently valid OMB control number.
Please do not return your form to the above organization. Send completed form to the Government Issuing Contracting Officer for the Contract/PR No. listed in Block E.
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16. REMARKS: Changes to office symbols, when necessary, shall be made by the CO/ACO without revisions to the CDRL.
BLOCK 9:
Distribution Statement D: (see paras 5.3 & 5.4 of instructions for 
distribution statement, warning, and destruction notices, and CUI marking 
requirements).

Blocks 10 - 13: 
Prepare the Quantity Data Report in accordance with DI-MGMT-82164 
and the OSD CAPE Deputy Director, Cost Assessment (DDCA)
-approved contract CSDR Plan. The DID, DI-MGMT-82164, is 
available from the Cost Assessment Data Enterprise (CADE) website at 
https://cade.osd.mil/policy/dids. The CSDR Plan is included as a contract 
attachment.  Official Approval of the 
deliverables is through OSD CAPE/DCARC. The approvals are shown as 
“Accepted” and “Finalized” in the CADE database.

The following tailoring of the DID is acceptable:
N/A

Contractors shall be required to submit the Quantity Data Report at 
frequencies specified in the CAPE-approved CSDR plan. The Government 
will be allowed 30 business days, after receipt from contractor, to review for approval/disapproval/comments. Contractor shall submit updated Quantity 
Data Report, incorporating Government comments, if applicable, NLT 30 
business days after receipt from Government. 
 The contract CSDR plan uses the event field as the driver for the 
submission of the reports, not the "as of date." If the event slips, the 
contractor must notify the Government Program Office that a date change is 
needed. It is the responsibility of the Government Program Office to submit 
a request for change in the event-driven date for reporting through the 
CADE website for CAPE approval before relief is given for the date 
reflected in the CAPE-approved CSDR Plan.

The Quantity Date Report shall be delivered in either a) MS Excel (.xlsx) 
or comma separated values (.csv) in accordance with the Quantity 
cPet-compatible template and the DD FORM 2794 or b) JavaScript 
Object Notation (JSON) as described in the Quantity Data Report 
Format Specification (FFS) and Data Exchange Instructions (DEI) 
referenced in the Quantity Data Report DID Requirements Section 2 and 
available on the CADE website at https://cade.osd.mil.

All files shall be submitted electronically using the CADE website. Data 
submitters must register through the CADE website and possess a 
DoD-approved ECA digital certificate or DoD-issued CAC to obtain 
a CADE Portal account and be authorized to upload CSDR content. Users 
can obtain access by submitting user information about themselves and their 
organizations to the CADE Portal and requesting a CSDR submitter user 
role. After the registration information has been verified, CAPE shall 
authorize the user account and requested roles. All CADE Portal accounts 
need to be renewed at least annually. 

Subcontractor Reporting: Prime contractors shall ensure CSDR requirements 
contained in their prime contracts are flowed down to all subcontractors who 
meet the reporting thresholds specified in the DoDI 5000.73, or as required 
by the cost working integrated product team (CWIPT). This includes 
requiring subcontractors to electronically report directly to CAPE using
See continuation sheet...
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16. REMARKS  (Continued)
the CSDR Submit-Review System.

The prime contractor shall be required to work with the CWIPT and all appropriate subcontractors to prepare separate 
subcontract CSDR plans for submission to the CAPE for DDCA approval. 

The Office of the Secretary of Defense (OSD) Cost Assessment & Program Evaluation (CAPE) may use a CADE 
management support contractor to review the data submitted under this CDRL to ensure contractual requirements are met 
and to facilitate distribution of the data to authorized Government users (hereinafter referred to as "the support 
contractor").  This data may include information that is considered a trade secret, proprietary, business sensitive, or 
otherwise protected pursuant to law or regulation (hereinafter referred to as “protected information”).  Execution of 
this contract by the contractor is considered consent to CAPE''s permitting access to any information, irrespective 
of restrictive markings or the nature of the information submitted, by its CADE management support contractor for the 
limited purpose of executing its CADE management support contract responsibilities.

BLOCK 14:  
Contractor shall submit a letter of delivery of Quantity Data Report to TopVue https://icbm.topvue.com/topvue-icbm/ 
and deliver electronically the report to CADE’s website https://cade.osd.mil/.
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INSTRUCTIONS FOR COMPLETING DD FORM 1423
(See DOD 5010.12-M for detailed instructions)

	FOR GOVERNMENT PERSONNEL

Item A. Self-explanatory.

Item B. Self-explanatory.

Item C. Mark (X) appropriate category: TDP - Technical Data Package; TM- Technical Manual; Other - other category of data such as “Provisioning,” “Configuration Management”, etc.

Item D. Enter name of system/item being acquired that data will support.

Item E. Self-Explanatory (to be filled in after award of contract).

Item F. Self-Explanatory (to be filled in after award of contract).

Item G. Signature of preparer of CDRL.

Item H. Date CDRL was prepared.

Item I. Signature of CDRL approval authority.

Item J. Date CDRL was approved.

Item 1. See DoD FAR Supplement Subpart 4.71 for proper numbering.

Item 2. Enter title as it appears on data acquisition document cited in Item 4.

Item 3. Enter subtitle of data item for further definition of data item (optional entry).

Item 4. Enter Data Item Description (DID) number, military specification number, or military standard number listed in DoD 5012.12-L (AMSDL), or one-time DID number, that defines data content and format requirements.

Item 5. Enter reference to tasking in contract that generates requirement for the date item (e.g. Statement of Work paragraph number).

Item 6. Enter technical office responsible for ensuring adequacy of the data item.

Item 7. Specify requirement for inspection/acceptance of the data item by the Government.

Item 8. Specify requirement for approval of a draft before preparation of the final data item.

Item 9. For technical data, specify requirement for contractor to mark the appropriate distribution statement of the data (ref: DoDD 5230.24)

Item 10. Specify number of times data items are to be delivered.

Item 11. Specify as-of-date of date item, when applicable.

Item 12. Specify when first submittal is required.

Item 13. Specify when subsequent submittals are required, when applicable.

Item 14. Enter addressees and number of draft/final copies t be delivered to each addressee. Explain reproducible copies in item 16.

Item 15. Enter total number of draft/final copies to be delivered.

Item 16. Use for additional/clarifying information for Items 1 through 15. Examples are: Tailoring of documents cited in Item 4; Clarification of submittal dates in items 12 and 13; Explanation of reproducible copies in Item 14; Desired medium for delivery of the data item.

	FOR THE CONTRACTOR

Item 17.  Specify  appropriate  price  group   from   one  of   the  following  groups  of  effort  in  developing  estimated prices for each data item listed on the DD Form 1423.



     a. Group I .   Definition   -   Data   which is not otherwise essential to the contractor's   performance of   the   primary contracted effort (production, development, testing and such as "Provisioning," "Configuration Management", etc.            
  

	Estimated Price - Costs to be included under Group are those applicable to preparing and assembling the data item in conformance with Government requirements, and the administration and other expenses related to reproducing and delivering such data items to the Government.



	b. Group II.   Definition  -  Data which  is  essential  to  the performance of the primary contracted effort but  the  contractor  is  required  to  perform    additional  work  to  conform to Government   requirements  with   regard  to  depth  of   control,  format, frequency of submittal, preparation, control,  or   quality of the data item.


	Estimated Price - Costs to be included under Group II are those incurred over and above the cost of the essential data item without   conforming   to   Government   requirements,   and the administrative and other expenses related to reproducing and delivering such data item to the Government.                  



	c. Group III. Definition  -  Data  which  the contractor  must develop  for  his  internal  use  in  performance of  the   primary contracted effort and does not require any substantial change to conform to  Government requirements  with  regard to  depth  of content,  format,  frequency  of  submittal,  preparation,  control, and quality of the data item.


	Estimated Price - Costs to be included under Group III are the administrative and other expenses related to reproducing and delivering such data item to the Government.



	d. Group IV.   Definition - Data which is developed by the contractor as part of his normal operating procedures and his effort in supplying these data to the Government is minimal.


	Estimated Price   -   Group IV items should normally be shown on the DD Form 1423 at no cost.


Item 18.  For each data item, enter an amount equal to that portion of the total price which is estimated to be attributable to the production or development for the Government of that item of data. These estimated data prices shall be developed only   from those costs which will be incurred as a direct result of the   requirement to supply the data, over and above those costs which would otherwise be incurred in performance of the contract if no data were required. The estimated data prices shall not include any amount for rights in data. The Government's right to use  the  data  shall  be  governed  by  the  pertinent   provisions  of   the contract
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    Contract Data Requirements List (CDRL)   Program: FT3 Production Follow - On   Date:  24   April 2026   Version:  1   Date of Determination: (Contract Award Date unless otherwise specified on the CDRL)     1. Introduction    This document was developed in ac cordance with DOD MIL - STD 31000C   and  DODM  5010.12  Acquisition and Management of Contractor - Prepared   Data. This  represents the general requirements  for the Technical Data Package (TDP) for this program.    The purpose of this Attachment, Technical Data Package, is to define the data d eliverables   due for  this program , including the instructions for their development, and delivery. All specific delivery  instructions are specified on the CDRL forms or its digital (word, excel, pdf) equivalent.    2. General Guidelines   The CDRL form, Department of Defense (DD) Form 1423, specifies the data required to be delivered  to the Government, as well as the frequency and approval requirements. The Data Item Descriptions  (DIDs), listed on the CDRL form, were selected from the Acqui sition Streamlining and  Standardization Information System (ASSIST) and provide additional direction for data preparation .     3. Communications   Any correspondence related to requests for data delivery deviations and/or amendments, additions or  deletions to the CDRL form shall be addressed to the Procuring Contracting Officer (PCO) with a  courtesy copy to the Data Management Officer (DMO) (Air Forc e Nuclear Weapons Center  (AFNWC)/N I MED) and the cognizant Program Manager (PM). Copies of all forms and templates  noted in this file are available as requested from PM, DMO, or PCO.     4. Codes used in the DD Form 1423   All CDRLs require Government approval. The directions for submittal and approval of data are  indicated in  Blocks 7, 8, 9, 10, 11, 12, 13, 14, 15, and 16 of the DD Form 1423. Usually, the direction  is in the form of a code (explained below). The following abbreviations/codes are common usage  within AFNWC.     4.1 Block 7, DD Form 250 Requirements   Block 7 of the CDRL form indicates whether Procurement Quality Assurance (PQA) inspections and  acceptance of deliverable data by DD Form 250 is required. “Draft” copies submitted for advance  approval and “Preliminary Draft” copies submitted are exempt from   the DD Form 250 requirements.  Information copies of DD Form 250 to accompany each letter of transmittal for this category of data.    

