## CLIN structure
USACE CLIN | AFCEC CLIN/Sub-CLIN Number | Optional Task Item Number | Installation | Site | AFCEC CLIN/Sub-CLIN Description | Projected/Estimated Award Date (Pending availability of funding and bona fide need as determined by the Government. ALL OPTIONS EXPIRE 114 MONTHS AFTER CONTRACT AWARD)*1 | Price (Do Not Use Rounding)
| 0001 |  | N/A | N/A | Complete Project Management Plan (PMP)
0001 | 0001CA |  | N/A | N/A | Complete PMP | Base Year (2027)
0002 | 0001CB | 001 | N/A | N/A | Update PMP | Optional Task based on need
0003 | 0001CC | 002 | N/A | N/A | Update PMP | Optional Task based on need
0004 | 0001CD | 003 | N/A | N/A | Complete ORC Transition Plan | FY35
| 0002 |  | N/A | N/A | Develop Integrated Master Schedule (IMS)/Milestone Payment Schedule (MPS) and Update Monthly
0005 | 0002CA |  | N/A | N/A | Develop IMS/MPS and Update Monthly | Base Year (2027)
0006 | 0002CB | 004 | N/A | N/A | Update IMS/MPS Monthly | FY28
0007 | 0002CC | 005 | N/A | N/A | Update IMS/MPS Monthly | FY29
0008 | 0002CD | 006 | N/A | N/A | Update IMS/MPS Monthly | FY30
0009 | 0002CE | 007 | N/A | N/A | Update IMS/MPS Monthly | FY31
0010 | 0002CF | 008 | N/A | N/A | Update IMS/MPS Monthly | FY32
0011 | 0002CG | 009 | N/A | N/A | Update IMS/MPS Monthly | FY33
0012 | 0002CH | 010 | N/A | N/A | Update IMS/MPS Monthly | FY34
0013 | 0002CJ | 011 | N/A | N/A | Update IMS/MPS Monthly | FY35
0014 | 0002CK | 012 | N/A | N/A | Update IMS/MPS Monthly | FY36
| 0003 |  | Eglin AFB | N/A | Update Community Involvement Plan
0015 | 0003CA |  | Eglin AFB | All Open Sites (IRP, MMRP, PFAS, etc) | Update Community Involvement Plan | Base Year (2027)
0016 | 0003CB | 013 | Eglin AFB | All Open Sites (IRP, MMRP, PFAS, etc) | Update Community Involvement Plan | FY30
0017 | 0003CC | 014 | Eglin AFB | All Open Sites (IRP, MMRP, PFAS, etc) | Update Community Involvement Plan | FY33
0018 | 0003CD | 015 | Eglin AFB | All Open Sites (IRP, MMRP, PFAS, etc) | Update Community Involvement Plan | FY36
| 0004 |  | Eglin AFB | N/A | Complete IRP Basewide Quality Program Plans (QPP)
0019 | 0004CA |  | Eglin AFB | N/A | Complete IRP Basewide QPP | Base Year (2027)
0020 | 0004CB | 016 | Eglin AFB | N/A | Update IRP Basewide QPP | Optional Task based on need
0021 | 0004CC | 017 | Eglin AFB | N/A | Update IRP Basewide QPP | Optional Task based on need
| 0005 |  | Eglin AFB | N/A | Perform RCRA Corrective Action/Hazardous and Solid Waste Amendments (CA/HSWA) Permit Renewal and Modification
0022 | 0005CA | 018 | Eglin AFB | N/A | Perform RCRA CA/HSWA Permit Renewal | Optional Task
0023 | 0005CB | 019 | Eglin AFB | N/A | Perform RCRA CA/HSWA Permit Modification | Optional Task
| 0006 |  | Eglin AFB | N/A | Perform Well Abandonment
0024 | 0006CA | 020 | Eglin AFB | N/A | Abandon up to one hundred fifty-five (155) Basewide Wells | FY29
| 0007 |  | Eglin AFB | CF288 | Achieve Remedy In Place
0025 | 0007AA | 021 | Eglin AFB | CF288 | Achieve Supplemental Site Assessment | FY28
0026 | 0007AB | 022 | Eglin AFB | CF288 | Achieve Remedial Action Plan | Optional Task
0027 | 0007AC | 023 | Eglin AFB | CF288 | Achieve Remedy In Place | Optional Task
0028 | 0007CA | 024 | Eglin AFB | CF288 | Conduct RA-O in accordance with the approved DD/ROD | FY33 - Upon Completion of 0007AC(CLIN 0027)
0029 | 0007CB | 025 | Eglin AFB | CF288 | Conduct RA-O in accordance with the approved DD/ROD | FY34
0030 | 0007CC | 026 | Eglin AFB | CF288 | Conduct RA-O in accordance with the approved DD/ROD | FY35
0031 | 0007CD | 027 | Eglin AFB | CF288 | Conduct RA-O in accordance with the approved DD/ROD | FY36
| 0008 |  | Eglin AFB | DP009 | Conduct LTM
0032 | 0008CA |  | Eglin AFB | DP009 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0033 | 0008CB | 028 | Eglin AFB | DP009 | Conduct LTM in accordance with the approved DD/ROD | FY28
0034 | 0008CC | 029 | Eglin AFB | DP009 | Conduct LTM in accordance with the approved DD/ROD | FY29
0035 | 0008CD | 030 | Eglin AFB | DP009 | Conduct LTM in accordance with the approved DD/ROD | FY30
0036 | 0008CE | 031 | Eglin AFB | DP009 | Conduct LTM in accordance with the approved DD/ROD | FY31
0037 | 0008CF | 032 | Eglin AFB | DP009 | Conduct LTM in accordance with the approved DD/ROD | FY32
0038 | 0008CG | 033 | Eglin AFB | DP009 | Conduct LTM in accordance with the approved DD/ROD | FY33
0039 | 0008CH | 034 | Eglin AFB | DP009 | Conduct LTM in accordance with the approved DD/ROD | FY34
0040 | 0008CJ | 035 | Eglin AFB | DP009 | Conduct LTM in accordance with the approved DD/ROD | FY35
0041 | 0008CK | 036 | Eglin AFB | DP009 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0009 |  | Eglin AFB | DP084 | Conduct LTM
0042 | 0009CA |  | Eglin AFB | DP084 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0043 | 0009CB | 037 | Eglin AFB | DP084 | Conduct LTM in accordance with the approved DD/ROD | FY28
0044 | 0009CC | 038 | Eglin AFB | DP084 | Conduct LTM in accordance with the approved DD/ROD | FY29
0045 | 0009CD | 039 | Eglin AFB | DP084 | Conduct LTM in accordance with the approved DD/ROD | FY30
0046 | 0009CE | 040 | Eglin AFB | DP084 | Conduct LTM in accordance with the approved DD/ROD | FY31
0047 | 0009CF | 041 | Eglin AFB | DP084 | Conduct LTM in accordance with the approved DD/ROD | FY32
0048 | 0009CG | 042 | Eglin AFB | DP084 | Conduct LTM in accordance with the approved DD/ROD | FY33
0049 | 0009CH | 043 | Eglin AFB | DP084 | Conduct LTM in accordance with the approved DD/ROD | FY34
0050 | 0009CJ | 044 | Eglin AFB | DP084 | Conduct LTM in accordance with the approved DD/ROD | FY35
0051 | 0009CK | 045 | Eglin AFB | DP084 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0010 |  | Eglin AFB | DP261 | Conduct LTM
0052 | 0010CA |  | Eglin AFB | DP261 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0053 | 0010CB | 046 | Eglin AFB | DP261 | Conduct LTM in accordance with the approved DD/ROD | FY28
0054 | 0010CC | 047 | Eglin AFB | DP261 | Conduct LTM in accordance with the approved DD/ROD | FY29
0055 | 0010CD | 048 | Eglin AFB | DP261 | Conduct LTM in accordance with the approved DD/ROD | FY30
0056 | 0010CE | 049 | Eglin AFB | DP261 | Conduct LTM in accordance with the approved DD/ROD | FY31
0057 | 0010CF | 050 | Eglin AFB | DP261 | Conduct LTM in accordance with the approved DD/ROD | FY32
0058 | 0010CG | 051 | Eglin AFB | DP261 | Conduct LTM in accordance with the approved DD/ROD | FY33
0059 | 0010CH | 052 | Eglin AFB | DP261 | Conduct LTM in accordance with the approved DD/ROD | FY34
0060 | 0010CJ | 053 | Eglin AFB | DP261 | Conduct LTM in accordance with the approved DD/ROD | FY35
0061 | 0010CK | 054 | Eglin AFB | DP261 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0011 |  | Eglin AFB | FT028 | Conduct LTM
0062 | 0011CA |  | Eglin AFB | FT028 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0063 | 0011CB | 055 | Eglin AFB | FT028 | Conduct LTM in accordance with the approved DD/ROD | FY28
0064 | 0011CC | 056 | Eglin AFB | FT028 | Conduct LTM in accordance with the approved DD/ROD | FY29
0065 | 0011CD | 057 | Eglin AFB | FT028 | Conduct LTM in accordance with the approved DD/ROD | FY30
0066 | 0011CE | 058 | Eglin AFB | FT028 | Conduct LTM in accordance with the approved DD/ROD | FY31
0067 | 0011CF | 059 | Eglin AFB | FT028 | Conduct LTM in accordance with the approved DD/ROD | FY32
0068 | 0011CG | 060 | Eglin AFB | FT028 | Conduct LTM in accordance with the approved DD/ROD | FY33
0069 | 0011CH | 061 | Eglin AFB | FT028 | Conduct LTM in accordance with the approved DD/ROD | FY34
0070 | 0011CJ | 062 | Eglin AFB | FT028 | Conduct LTM in accordance with the approved DD/ROD | FY35
0071 | 0011CK | 063 | Eglin AFB | FT028 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0012 |  | Eglin AFB | LF003 | Conduct RA-O
0072 | 0012CA |  | Eglin AFB | LF003 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0073 | 0012CB | 064 | Eglin AFB | LF003 | Conduct LTM in accordance with the approved DD/ROD | FY28
0074 | 0012CC | 065 | Eglin AFB | LF003 | Conduct LTM in accordance with the approved DD/ROD | FY29
0075 | 0012CD | 066 | Eglin AFB | LF003 | Conduct LTM in accordance with the approved DD/ROD | FY30
0076 | 0012CE | 067 | Eglin AFB | LF003 | Conduct LTM in accordance with the approved DD/ROD | FY31
0077 | 0012CF | 068 | Eglin AFB | LF003 | Conduct LTM in accordance with the approved DD/ROD | FY32
0078 | 0012CG | 069 | Eglin AFB | LF003 | Conduct LTM in accordance with the approved DD/ROD | FY33
0079 | 0012CH | 070 | Eglin AFB | LF003 | Conduct LTM in accordance with the approved DD/ROD | FY34
0080 | 0012CJ | 071 | Eglin AFB | LF003 | Conduct LTM in accordance with the approved DD/ROD | FY35
0081 | 0012CK | 072 | Eglin AFB | LF003 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0013 |  | Eglin AFB | LF005 | Conduct LTM
0082 | 0013CA |  | Eglin AFB | LF005 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0083 | 0013CB | 073 | Eglin AFB | LF005 | Conduct LTM in accordance with the approved DD/ROD | FY28
0084 | 0013CC | 074 | Eglin AFB | LF005 | Conduct LTM in accordance with the approved DD/ROD | FY29
0085 | 0013CD | 075 | Eglin AFB | LF005 | Conduct LTM in accordance with the approved DD/ROD | FY30
0086 | 0013CE | 076 | Eglin AFB | LF005 | Conduct LTM in accordance with the approved DD/ROD | FY31
0087 | 0013CF | 077 | Eglin AFB | LF005 | Conduct LTM in accordance with the approved DD/ROD | FY32
0088 | 0013CG | 078 | Eglin AFB | LF005 | Conduct LTM in accordance with the approved DD/ROD | FY33
0089 | 0013CH | 079 | Eglin AFB | LF005 | Conduct LTM in accordance with the approved DD/ROD | FY34
0090 | 0013CJ | 080 | Eglin AFB | LF005 | Conduct LTM in accordance with the approved DD/ROD | FY35
0091 | 0013CK | 081 | Eglin AFB | LF005 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0014 |  | Eglin AFB | LF008 | Conduct LTM
0092 | 0014CA |  | Eglin AFB | LF008 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0093 | 0014CB | 082 | Eglin AFB | LF008 | Conduct LTM in accordance with the approved DD/ROD | FY28
0094 | 0014CC | 083 | Eglin AFB | LF008 | Conduct LTM in accordance with the approved DD/ROD | FY29
0095 | 0014CD | 084 | Eglin AFB | LF008 | Conduct LTM in accordance with the approved DD/ROD | FY30
0096 | 0014CE | 085 | Eglin AFB | LF008 | Conduct LTM in accordance with the approved DD/ROD | FY31
0097 | 0014CF | 086 | Eglin AFB | LF008 | Conduct LTM in accordance with the approved DD/ROD | FY32
0098 | 0014CG | 087 | Eglin AFB | LF008 | Conduct LTM in accordance with the approved DD/ROD | FY33
0099 | 0014CH | 088 | Eglin AFB | LF008 | Conduct LTM in accordance with the approved DD/ROD | FY34
0100 | 0014CJ | 089 | Eglin AFB | LF008 | Conduct LTM in accordance with the approved DD/ROD | FY35
0101 | 0014CK | 090 | Eglin AFB | LF008 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0015 |  | Eglin AFB | LF010 | Conduct LTM
0102 | 0015CA |  | Eglin AFB | LF010 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0103 | 0015CB | 091 | Eglin AFB | LF010 | Conduct LTM in accordance with the approved DD/ROD | FY28
0104 | 0015CC | 092 | Eglin AFB | LF010 | Conduct LTM in accordance with the approved DD/ROD | FY29
0105 | 0015CD | 093 | Eglin AFB | LF010 | Conduct LTM in accordance with the approved DD/ROD | FY30
0106 | 0015CE | 094 | Eglin AFB | LF010 | Conduct LTM in accordance with the approved DD/ROD | FY31
0107 | 0015CF | 095 | Eglin AFB | LF010 | Conduct LTM in accordance with the approved DD/ROD | FY32
0108 | 0015CG | 096 | Eglin AFB | LF010 | Conduct LTM in accordance with the approved DD/ROD | FY33
0109 | 0015CH | 097 | Eglin AFB | LF010 | Conduct LTM in accordance with the approved DD/ROD | FY34
0110 | 0015CJ | 098 | Eglin AFB | LF010 | Conduct LTM in accordance with the approved DD/ROD | FY35
0111 | 0015CK | 099 | Eglin AFB | LF010 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0016 |  | Eglin AFB | LF051 | Conduct LTM
0112 | 0016CA |  | Eglin AFB | LF051 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0113 | 0016CB | 100 | Eglin AFB | LF051 | Conduct LTM in accordance with the approved DD/ROD | FY28
0114 | 0016CC | 101 | Eglin AFB | LF051 | Conduct LTM in accordance with the approved DD/ROD | FY29
0115 | 0016CD | 102 | Eglin AFB | LF051 | Conduct LTM in accordance with the approved DD/ROD | FY30
0116 | 0016CE | 103 | Eglin AFB | LF051 | Conduct LTM in accordance with the approved DD/ROD | FY31
0117 | 0016CF | 104 | Eglin AFB | LF051 | Conduct LTM in accordance with the approved DD/ROD | FY32
0118 | 0016CG | 105 | Eglin AFB | LF051 | Conduct LTM in accordance with the approved DD/ROD | FY33
0119 | 0016CH | 106 | Eglin AFB | LF051 | Conduct LTM in accordance with the approved DD/ROD | FY34
0120 | 0016CJ | 107 | Eglin AFB | LF051 | Conduct LTM in accordance with the approved DD/ROD | FY35
0121 | 0016CK | 108 | Eglin AFB | LF051 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0017 |  | Eglin AFB | LF322 | Achieve Site Assessment
0122 | 0017AA | 109 | Eglin AFB | LF322 | Achieve Site Assessment | FY29
| 0018 |  | Eglin AFB | OT083 | Conduct LTM
0123 | 0018CA |  | Eglin AFB | OT083 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0124 | 0018CB | 110 | Eglin AFB | OT083 | Conduct LTM in accordance with the approved DD/ROD | FY28
0125 | 0018CC | 111 | Eglin AFB | OT083 | Conduct LTM in accordance with the approved DD/ROD | FY29
0126 | 0018CD | 112 | Eglin AFB | OT083 | Conduct LTM in accordance with the approved DD/ROD | FY30
0127 | 0018CE | 113 | Eglin AFB | OT083 | Conduct LTM in accordance with the approved DD/ROD | FY31
0128 | 0018CF | 114 | Eglin AFB | OT083 | Conduct LTM in accordance with the approved DD/ROD | FY32
0129 | 0018CG | 115 | Eglin AFB | OT083 | Conduct LTM in accordance with the approved DD/ROD | FY33
0130 | 0018CH | 116 | Eglin AFB | OT083 | Conduct LTM in accordance with the approved DD/ROD | FY34
0131 | 0018CJ | 117 | Eglin AFB | OT083 | Conduct LTM in accordance with the approved DD/ROD | FY35
0132 | 0018CK | 118 | Eglin AFB | OT083 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0019 |  | Eglin AFB | OT100 | Conduct LTM
0133 | 0019CA |  | Eglin AFB | OT100 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0134 | 0019CB | 119 | Eglin AFB | OT100 | Conduct LTM in accordance with the approved DD/ROD | FY28
0135 | 0019CC | 120 | Eglin AFB | OT100 | Conduct LTM in accordance with the approved DD/ROD | FY29
0136 | 0019CD | 121 | Eglin AFB | OT100 | Conduct LTM in accordance with the approved DD/ROD | FY30
0137 | 0019CE | 122 | Eglin AFB | OT100 | Conduct LTM in accordance with the approved DD/ROD | FY31
0138 | 0019CF | 123 | Eglin AFB | OT100 | Conduct LTM in accordance with the approved DD/ROD | FY32
0139 | 0019CG | 124 | Eglin AFB | OT100 | Conduct LTM in accordance with the approved DD/ROD | FY33
0140 | 0019CH | 125 | Eglin AFB | OT100 | Conduct LTM in accordance with the approved DD/ROD | FY34
0141 | 0019CJ | 126 | Eglin AFB | OT100 | Conduct LTM in accordance with the approved DD/ROD | FY35
0142 | 0019CK | 127 | Eglin AFB | OT100 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0020 |  | Eglin AFB | OT262 | Conduct LTM
0143 | 0020CA |  | Eglin AFB | OT262 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0144 | 0020CB | 128 | Eglin AFB | OT262 | Conduct LTM in accordance with the approved DD/ROD | FY28
0145 | 0020CC | 129 | Eglin AFB | OT262 | Conduct LTM in accordance with the approved DD/ROD | FY29
0146 | 0020CD | 130 | Eglin AFB | OT262 | Conduct LTM in accordance with the approved DD/ROD | FY30
0147 | 0020CE | 131 | Eglin AFB | OT262 | Conduct LTM in accordance with the approved DD/ROD | FY31
0148 | 0020CF | 132 | Eglin AFB | OT262 | Conduct LTM in accordance with the approved DD/ROD | FY32
0149 | 0020CG | 133 | Eglin AFB | OT262 | Conduct LTM in accordance with the approved DD/ROD | FY33
0150 | 0020CH | 134 | Eglin AFB | OT262 | Conduct LTM in accordance with the approved DD/ROD | FY34
0151 | 0020CJ | 135 | Eglin AFB | OT262 | Conduct LTM in accordance with the approved DD/ROD | FY35
0152 | 0020CK | 136 | Eglin AFB | OT262 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0021 |  | Eglin AFB | OT263 | Conduct LTM
0153 | 0021CA |  | Eglin AFB | OT263 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0154 | 0021CB | 137 | Eglin AFB | OT263 | Conduct LTM in accordance with the approved DD/ROD | FY28
0155 | 0021CC | 138 | Eglin AFB | OT263 | Conduct LTM in accordance with the approved DD/ROD | FY29
0156 | 0021CD | 139 | Eglin AFB | OT263 | Conduct LTM in accordance with the approved DD/ROD | FY30
0157 | 0021CE | 140 | Eglin AFB | OT263 | Conduct LTM in accordance with the approved DD/ROD | FY31
0158 | 0021CF | 141 | Eglin AFB | OT263 | Conduct LTM in accordance with the approved DD/ROD | FY32
0159 | 0021CG | 142 | Eglin AFB | OT263 | Conduct LTM in accordance with the approved DD/ROD | FY33
0160 | 0021CH | 143 | Eglin AFB | OT263 | Conduct LTM in accordance with the approved DD/ROD | FY34
0161 | 0021CJ | 144 | Eglin AFB | OT263 | Conduct LTM in accordance with the approved DD/ROD | FY35
0162 | 0021CK | 145 | Eglin AFB | OT263 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0022 |  | Eglin AFB | OT264 | Conduct LTM
0163 | 0022CA |  | Eglin AFB | OT264 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0164 | 0022CB | 146 | Eglin AFB | OT264 | Conduct LTM in accordance with the approved DD/ROD | FY28
0165 | 0022CC | 147 | Eglin AFB | OT264 | Conduct LTM in accordance with the approved DD/ROD | FY29
0166 | 0022CD | 148 | Eglin AFB | OT264 | Conduct LTM in accordance with the approved DD/ROD | FY30
0167 | 0022CE | 149 | Eglin AFB | OT264 | Conduct LTM in accordance with the approved DD/ROD | FY31
0168 | 0022CF | 150 | Eglin AFB | OT264 | Conduct LTM in accordance with the approved DD/ROD | FY32
0169 | 0022CG | 151 | Eglin AFB | OT264 | Conduct LTM in accordance with the approved DD/ROD | FY33
0170 | 0022CH | 152 | Eglin AFB | OT264 | Conduct LTM in accordance with the approved DD/ROD | FY34
0171 | 0022CJ | 153 | Eglin AFB | OT264 | Conduct LTM in accordance with the approved DD/ROD | FY35
0172 | 0022CK | 154 | Eglin AFB | OT264 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0023 |  | Eglin AFB | OT265 | Conduct LTM
0173 | 0023CA |  | Eglin AFB | OT265 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0174 | 0023CB | 155 | Eglin AFB | OT265 | Conduct LTM in accordance with the approved DD/ROD | FY28
0175 | 0023CC | 156 | Eglin AFB | OT265 | Conduct LTM in accordance with the approved DD/ROD | FY29
0176 | 0023CD | 157 | Eglin AFB | OT265 | Conduct LTM in accordance with the approved DD/ROD | FY30
0177 | 0023CE | 158 | Eglin AFB | OT265 | Conduct LTM in accordance with the approved DD/ROD | FY31
0178 | 0023CF | 159 | Eglin AFB | OT265 | Conduct LTM in accordance with the approved DD/ROD | FY32
0179 | 0023CG | 160 | Eglin AFB | OT265 | Conduct LTM in accordance with the approved DD/ROD | FY33
0180 | 0023CH | 161 | Eglin AFB | OT265 | Conduct LTM in accordance with the approved DD/ROD | FY34
0181 | 0023CJ | 162 | Eglin AFB | OT265 | Conduct LTM in accordance with the approved DD/ROD | FY35
0182 | 0023CK | 163 | Eglin AFB | OT265 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0024 |  | Eglin AFB | OT269 | Conduct LTM
0183 | 0024CA |  | Eglin AFB | OT269 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0184 | 0024CB | 164 | Eglin AFB | OT269 | Conduct LTM in accordance with the approved DD/ROD | FY28
0185 | 0024CC | 165 | Eglin AFB | OT269 | Conduct LTM in accordance with the approved DD/ROD | FY29
0186 | 0024CD | 166 | Eglin AFB | OT269 | Conduct LTM in accordance with the approved DD/ROD | FY30
0187 | 0024CE | 167 | Eglin AFB | OT269 | Conduct LTM in accordance with the approved DD/ROD | FY31
0188 | 0024CF | 168 | Eglin AFB | OT269 | Conduct LTM in accordance with the approved DD/ROD | FY32
0189 | 0024CG | 169 | Eglin AFB | OT269 | Conduct LTM in accordance with the approved DD/ROD | FY33
0190 | 0024CH | 170 | Eglin AFB | OT269 | Conduct LTM in accordance with the approved DD/ROD | FY34
0191 | 0024CJ | 171 | Eglin AFB | OT269 | Conduct LTM in accordance with the approved DD/ROD | FY35
0192 | 0024CK | 172 | Eglin AFB | OT269 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0025 |  | Eglin AFB | OT270 | Conduct LTM
0193 | 0025CA |  | Eglin AFB | OT270 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0194 | 0025CB | 173 | Eglin AFB | OT270 | Conduct LTM in accordance with the approved DD/ROD | FY28
0195 | 0025CC | 174 | Eglin AFB | OT270 | Conduct LTM in accordance with the approved DD/ROD | FY29
0196 | 0025CD | 175 | Eglin AFB | OT270 | Conduct LTM in accordance with the approved DD/ROD | FY30
0197 | 0025CE | 176 | Eglin AFB | OT270 | Conduct LTM in accordance with the approved DD/ROD | FY31
0198 | 0025CF | 177 | Eglin AFB | OT270 | Conduct LTM in accordance with the approved DD/ROD | FY32
0199 | 0025CG | 178 | Eglin AFB | OT270 | Conduct LTM in accordance with the approved DD/ROD | FY33
0200 | 0025CH | 179 | Eglin AFB | OT270 | Conduct LTM in accordance with the approved DD/ROD | FY34
0201 | 0025CJ | 180 | Eglin AFB | OT270 | Conduct LTM in accordance with the approved DD/ROD | FY35
0202 | 0025CK | 181 | Eglin AFB | OT270 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0026 |  | Eglin AFB | OT271 | Conduct LTM
0203 | 0026CA |  | Eglin AFB | OT271 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0204 | 0026CB | 182 | Eglin AFB | OT271 | Conduct LTM in accordance with the approved DD/ROD | FY28
0205 | 0026CC | 183 | Eglin AFB | OT271 | Conduct LTM in accordance with the approved DD/ROD | FY29
0206 | 0026CD | 184 | Eglin AFB | OT271 | Conduct LTM in accordance with the approved DD/ROD | FY30
0207 | 0026CE | 185 | Eglin AFB | OT271 | Conduct LTM in accordance with the approved DD/ROD | FY31
0208 | 0026CF | 186 | Eglin AFB | OT271 | Conduct LTM in accordance with the approved DD/ROD | FY32
0209 | 0026CG | 187 | Eglin AFB | OT271 | Conduct LTM in accordance with the approved DD/ROD | FY33
0210 | 0026CH | 188 | Eglin AFB | OT271 | Conduct LTM in accordance with the approved DD/ROD | FY34
0211 | 0026CJ | 189 | Eglin AFB | OT271 | Conduct LTM in accordance with the approved DD/ROD | FY35
0212 | 0026CK | 190 | Eglin AFB | OT271 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0027 |  | Eglin AFB | POI523 | Conduct LTM
0213 | 0027CA |  | Eglin AFB | POI523 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0214 | 0027CB | 191 | Eglin AFB | POI523 | Conduct LTM in accordance with the approved DD/ROD | FY28
0215 | 0027CC | 192 | Eglin AFB | POI523 | Conduct LTM in accordance with the approved DD/ROD | FY29
0216 | 0027CD | 193 | Eglin AFB | POI523 | Conduct LTM in accordance with the approved DD/ROD | FY30
0217 | 0027CE | 194 | Eglin AFB | POI523 | Conduct LTM in accordance with the approved DD/ROD | FY31
0218 | 0027CF | 195 | Eglin AFB | POI523 | Conduct LTM in accordance with the approved DD/ROD | FY32
0219 | 0027CG | 196 | Eglin AFB | POI523 | Conduct LTM in accordance with the approved DD/ROD | FY33
0220 | 0027CH | 197 | Eglin AFB | POI523 | Conduct LTM in accordance with the approved DD/ROD | FY34
0221 | 0027CJ | 198 | Eglin AFB | POI523 | Conduct LTM in accordance with the approved DD/ROD | FY35
0222 | 0027CK | 199 | Eglin AFB | POI523 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0028 |  | Eglin AFB | SS025 | Conduct LTM
0223 | 0028CA |  | Eglin AFB | SS025 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0224 | 0028CB | 200 | Eglin AFB | SS025 | Conduct LTM in accordance with the approved DD/ROD | FY28
0225 | 0028CC | 201 | Eglin AFB | SS025 | Conduct LTM in accordance with the approved DD/ROD | FY29
0226 | 0028CD | 202 | Eglin AFB | SS025 | Conduct LTM in accordance with the approved DD/ROD | FY30
0227 | 0028CE | 203 | Eglin AFB | SS025 | Conduct LTM in accordance with the approved DD/ROD | FY31
0228 | 0028CF | 204 | Eglin AFB | SS025 | Conduct LTM in accordance with the approved DD/ROD | FY32
0229 | 0028CG | 205 | Eglin AFB | SS025 | Conduct LTM in accordance with the approved DD/ROD | FY33
0230 | 0028CH | 206 | Eglin AFB | SS025 | Conduct LTM in accordance with the approved DD/ROD | FY34
0231 | 0028CJ | 207 | Eglin AFB | SS025 | Conduct LTM in accordance with the approved DD/ROD | FY35
0232 | 0028CK | 208 | Eglin AFB | SS025 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0029 |  | Eglin AFB | SS026 | Conduct LTM
0233 | 0029CA |  | Eglin AFB | SS026 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0234 | 0029CB | 209 | Eglin AFB | SS026 | Conduct LTM in accordance with the approved DD/ROD | FY28
0235 | 0029CC | 210 | Eglin AFB | SS026 | Conduct LTM in accordance with the approved DD/ROD | FY29
0236 | 0029CD | 211 | Eglin AFB | SS026 | Conduct LTM in accordance with the approved DD/ROD | FY30
0237 | 0029CE | 212 | Eglin AFB | SS026 | Conduct LTM in accordance with the approved DD/ROD | FY31
0238 | 0029CF | 213 | Eglin AFB | SS026 | Conduct LTM in accordance with the approved DD/ROD | FY32
0239 | 0029CG | 214 | Eglin AFB | SS026 | Conduct LTM in accordance with the approved DD/ROD | FY33
0240 | 0029CH | 215 | Eglin AFB | SS026 | Conduct LTM in accordance with the approved DD/ROD | FY34
0241 | 0029CJ | 216 | Eglin AFB | SS026 | Conduct LTM in accordance with the approved DD/ROD | FY25
0242 | 0029CK | 217 | Eglin AFB | SS026 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0030 |  | Eglin AFB | SS086 | Conduct LTM
0243 | 0030CA |  | Eglin AFB | SS086 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0244 | 0030CB | 218 | Eglin AFB | SS086 | Conduct LTM in accordance with the approved DD/ROD | FY28
0245 | 0030CC | 219 | Eglin AFB | SS086 | Conduct LTM in accordance with the approved DD/ROD | FY29
0246 | 0030CD | 220 | Eglin AFB | SS086 | Conduct LTM in accordance with the approved DD/ROD | FY30
0247 | 0030CE | 221 | Eglin AFB | SS086 | Conduct LTM in accordance with the approved DD/ROD | FY31
0248 | 0030CF | 222 | Eglin AFB | SS086 | Conduct LTM in accordance with the approved DD/ROD | FY32
0249 | 0030CG | 223 | Eglin AFB | SS086 | Conduct LTM in accordance with the approved DD/ROD | FY33
0250 | 0030CH | 224 | Eglin AFB | SS086 | Conduct LTM in accordance with the approved DD/ROD | FY34
0251 | 0030CJ | 225 | Eglin AFB | SS086 | Conduct LTM in accordance with the approved DD/ROD | FY35
0252 | 0030CK | 226 | Eglin AFB | SS086 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0031 |  | Eglin AFB | SS278 | Conduct LTM
0253 | 0031CA |  | Eglin AFB | SS278 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0254 | 0031CB | 227 | Eglin AFB | SS278 | Conduct LTM in accordance with the approved DD/ROD | FY28
0255 | 0031CC | 228 | Eglin AFB | SS278 | Conduct LTM in accordance with the approved DD/ROD | FY29
0256 | 0031CD | 229 | Eglin AFB | SS278 | Conduct LTM in accordance with the approved DD/ROD | FY30
0257 | 0031CE | 230 | Eglin AFB | SS278 | Conduct LTM in accordance with the approved DD/ROD | FY31
0258 | 0031CF | 231 | Eglin AFB | SS278 | Conduct LTM in accordance with the approved DD/ROD | FY32
0259 | 0031CG | 232 | Eglin AFB | SS278 | Conduct LTM in accordance with the approved DD/ROD | FY33
0260 | 0031CH | 233 | Eglin AFB | SS278 | Conduct LTM in accordance with the approved DD/ROD | FY34
0261 | 0031CJ | 234 | Eglin AFB | SS278 | Conduct LTM in accordance with the approved DD/ROD | FY35
0262 | 0031CK | 235 | Eglin AFB | SS278 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0032 |  | Eglin AFB | SS281 | Conduct LTM
0263 | 0032CA |  | Eglin AFB | SS281 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0264 | 0032CB | 236 | Eglin AFB | SS281 | Conduct LTM in accordance with the approved DD/ROD | FY28
0265 | 0032CC | 237 | Eglin AFB | SS281 | Conduct LTM in accordance with the approved DD/ROD | FY29
0266 | 0032CD | 238 | Eglin AFB | SS281 | Conduct LTM in accordance with the approved DD/ROD | FY30
0267 | 0032CE | 239 | Eglin AFB | SS281 | Conduct LTM in accordance with the approved DD/ROD | FY31
0268 | 0032CF | 240 | Eglin AFB | SS281 | Conduct LTM in accordance with the approved DD/ROD | FY32
0269 | 0032CG | 241 | Eglin AFB | SS281 | Conduct LTM in accordance with the approved DD/ROD | FY33
0270 | 0032CH | 242 | Eglin AFB | SS281 | Conduct LTM in accordance with the approved DD/ROD | FY34
0271 | 0032CJ | 243 | Eglin AFB | SS281 | Conduct LTM in accordance with the approved DD/ROD | FY35
0272 | 0032CK | 244 | Eglin AFB | SS281 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0033 |  | Eglin AFB | SS283 | Conduct LTM
0273 | 0033CA |  | Eglin AFB | SS283 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0274 | 0033CB | 245 | Eglin AFB | SS283 | Conduct LTM in accordance with the approved DD/ROD | FY28
0275 | 0033CC | 246 | Eglin AFB | SS283 | Conduct LTM in accordance with the approved DD/ROD | FY29
0276 | 0033CD | 247 | Eglin AFB | SS283 | Conduct LTM in accordance with the approved DD/ROD | FY30
0277 | 0033CE | 248 | Eglin AFB | SS283 | Conduct LTM in accordance with the approved DD/ROD | FY31
0278 | 0033CF | 249 | Eglin AFB | SS283 | Conduct LTM in accordance with the approved DD/ROD | FY32
0279 | 0033CG | 250 | Eglin AFB | SS283 | Conduct LTM in accordance with the approved DD/ROD | FY33
0280 | 0033CH | 251 | Eglin AFB | SS283 | Conduct LTM in accordance with the approved DD/ROD | FY34
0281 | 0033CJ | 252 | Eglin AFB | SS283 | Conduct LTM in accordance with the approved DD/ROD | FY35
0282 | 0033CK | 253 | Eglin AFB | SS283 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0034 |  | Eglin AFB | SS313 | Achieve Site Closeout
0283 | 0034AA | 254 | Eglin AFB | SS313 | Achieve Remedial Action | FY28
0284 | 0034AB | 255 | Eglin AFB | SS313 | Achieve Site Closeout | Optional Task based on need
| 0035 |  | Eglin AFB | ST069 | Achieve Response Complete
0285 | 0035AA | 256 | Eglin AFB | ST069 | Achieve Response Complete | FY28
0286 | 0035AB | 257 | Eglin AFB | ST069 | Achieve Conditional Site Closeout | Optional Task based on need
0287 | 0035CA |  | Eglin AFB | ST069 | Conduct RA-O in accordance with the approved DD / ROD | Base Year (2027)
0288 | 0035CB | 258 | Eglin AFB | ST069 | Conduct RA-O in accordance with the approved DD / ROD | FY28
0289 | 0035CC | 259 | Eglin AFB | ST069 | Conduct RA-O in accordance with the approved DD / ROD | FY29
0290 | 0035CD | 260 | Eglin AFB | ST069 | Conduct RA-O in accordance with the approved DD / ROD | FY30
0291 | 0035CE | 261 | Eglin AFB | ST069 | Conduct RA-O in accordance with the approved DD / ROD | FY31
0292 | 0035CF | 262 | Eglin AFB | ST069 | Conduct RA-O in accordance with the approved DD / ROD | FY32
0293 | 0035CG | 263 | Eglin AFB | ST069 | Conduct RA-O in accordance with the approved DD / ROD | FY33
0294 | 0035CH | 264 | Eglin AFB | ST069 | Conduct RA-O in accordance with the approved DD / ROD | FY34
0295 | 0035CJ | 265 | Eglin AFB | ST069 | Conduct LTM in accordance with the approved DD/ROD | FY35
0296 | 0035CK | 266 | Eglin AFB | ST069 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0036 |  | Hurlburt Field | N/A | Update Community Involvement Plan
0297 | 0036CA |  | Hurlburt Field | All Open Sites (IRP, MMRP, PFAS, etc) | Update Community Involvement Plan | Base Year (2027)
0298 | 0036CB | 267 | Hurlburt Field | All Open Sites (IRP, MMRP, PFAS, etc) | Update Community Involvement Plan | FY31
0299 | 0036CC | 268 | Hurlburt Field | All Open Sites (IRP, MMRP, PFAS, etc) | Update Community Involvement Plan | FY34
0300 | 0036CD | 269 | Hurlburt Field | All Open Sites (IRP, MMRP, PFAS, etc) | Update Community Involvement Plan | FY36
| 0037 |  | Hurlburt Field | N/A | Complete IRP Basewide Quality Program Plans (QPP)
0301 | 0037CA |  | Hurlburt Field | N/A | Complete IRP Basewide QPP | Base Year (2027)
0302 | 0037CB | 270 | Hurlburt Field | N/A | Update IRP Basewide QPP | Optional Task based on need
0303 | 0037CC | 271 | Hurlburt Field | N/A | Update IRP Basewide QPP | Optional Task based on need
| 0038 |  | Hurlburt Field | N/A | Complete MMRP Quality Program Plan (QPP)
0304 | 0038CA |  | Hurlburt Field | N/A | Complete MMRP QPP | Base Year (2027)
0305 | 0038CB | 272 | Hurlburt Field | N/A | Update MMRP QPP | Optional Task based on need
0306 | 0038CC | 273 | Hurlburt Field | N/A | Update MMRP QPP | Optional Task based on need
| 0039 |  | Hurlburt Field | N/A | Perform Well Survey, Inventory, and Condition Assessment
0307 | 0039CA | 274 | Hurlburt Field | N/A | Complete Well Survey, Inventory, and Condition Assessment | FY29
0308 | 0039CB | 275 | Hurlburt Field | N/A | Update Well Survey, Inventory, and Condition Assessment | FY33
| 0040 |  | Hurlburt Field | N/A | Perform RCRA Corrective Action/Hazardous and Solid Waste Amendments (CA/HWSA) Permit Renewal and Modification
0309 | 0040CA | 276 | Hurlburt Field | N/A | Perform RCRA CA/HSWA Permit Renewal | FY30
0310 | 0040CB | 277 | Hurlburt Field | N/A | Perform RCRA CA/HSWA Permit Modification | Optional Task based on need
| 0041 |  | Hurlburt Field | N/A | Perform Well Abandonment
0311 | 0041CA | 278 | Hurlburt Field | N/A | Abandon up to eighty-six (86) Basewide Wells | FY29
| 0042 |  | Hurlburt Field | CG219 | Achieve Remedy In Place
0312 | 0042AA |  | Hurlburt Field | CG219 | Achieve Supplemental Site Assessment | Base Year (2027)
0313 | 0042AB | 279 | Hurlburt Field | CG219 | Achieve Remedial Action Plan | Optional Task
0314 | 0042AC | 280 | Hurlburt Field | CG219 | Achieve Remedy In Place | Optional Task
0315 | 0042CA | 281 | Hurlburt Field | CG219 | Conduct RA-O in accordance with the approved DD / ROD | FY30 - Upon Completion of 0042AC (0314)
0316 | 0042CB | 282 | Hurlburt Field | CG219 | Conduct RA-O in accordance with the approved DD / ROD | FY31
0317 | 0042CC | 283 | Hurlburt Field | CG219 | Conduct RA-O in accordance with the approved DD / ROD | FY32
0318 | 0042CD | 284 | Hurlburt Field | CG219 | Conduct RA-O in accordance with the approved DD / ROD | FY33
0319 | 0042CE | 285 | Hurlburt Field | CG219 | Conduct RA-O in accordance with the approved DD / ROD | FY34
0320 | 0042CF | 286 | Hurlburt Field | CG219 | Conduct RA-O in accordance with the approved DD / ROD | FY35
0321 | 0042CG | 287 | Hurlburt Field | CG219 | Conduct RA-O in accordance with the approved DD / ROD | FY36
| 0043 |  | Hurlburt Field | LF013 | Conduct LTM
0322 | 0043CA |  | Hurlburt Field | LF013 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0323 | 0043CB | 288 | Hurlburt Field | LF013 | Conduct LTM in accordance with the approved DD/ROD | FY28
0324 | 0043CC | 289 | Hurlburt Field | LF013 | Conduct LTM in accordance with the approved DD/ROD | FY29
0325 | 0043CD | 290 | Hurlburt Field | LF013 | Conduct LTM in accordance with the approved DD/ROD | FY30
0326 | 0043CE | 291 | Hurlburt Field | LF013 | Conduct LTM in accordance with the approved DD/ROD | FY31
0327 | 0043CF | 292 | Hurlburt Field | LF013 | Conduct LTM in accordance with the approved DD/ROD | FY32
0328 | 0043CG | 293 | Hurlburt Field | LF013 | Conduct LTM in accordance with the approved DD/ROD | FY33
0329 | 0043CH | 294 | Hurlburt Field | LF013 | Conduct LTM in accordance with the approved DD/ROD | FY34
0330 | 0043CJ | 295 | Hurlburt Field | LF013 | Conduct LTM in accordance with the approved DD/ROD | FY35
0331 | 0043CK | 296 | Hurlburt Field | LF013 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0044 |  | Hurlburt Field | LF014 | Conduct LTM
0332 | 0044CA |  | Hurlburt Field | LF014 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0333 | 0044CB | 297 | Hurlburt Field | LF014 | Conduct LTM in accordance with the approved DD/ROD | FY28
0334 | 0044CC | 298 | Hurlburt Field | LF014 | Conduct LTM in accordance with the approved DD/ROD | FY29
0335 | 0044CD | 299 | Hurlburt Field | LF014 | Conduct LTM in accordance with the approved DD/ROD | FY30
0336 | 0044CE | 300 | Hurlburt Field | LF014 | Conduct LTM in accordance with the approved DD/ROD | FY31
0337 | 0044CF | 301 | Hurlburt Field | LF014 | Conduct LTM in accordance with the approved DD/ROD | FY32
0338 | 0044CG | 302 | Hurlburt Field | LF014 | Conduct LTM in accordance with the approved DD/ROD | FY33
0339 | 0044CH | 303 | Hurlburt Field | LF014 | Conduct LTM in accordance with the approved DD/ROD | FY34
0340 | 0044CJ | 304 | Hurlburt Field | LF014 | Conduct LTM in accordance with the approved DD/ROD | FY35
0341 | 0044CK | 305 | Hurlburt Field | LF014 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0045 |  | Hurlburt Field | LF015 | Conduct LTM
0342 | 0045CA |  | Hurlburt Field | LF015 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0343 | 0045CB | 306 | Hurlburt Field | LF015 | Conduct LTM in accordance with the approved DD/ROD | FY28
0344 | 0045CC | 307 | Hurlburt Field | LF015 | Conduct LTM in accordance with the approved DD/ROD | FY29
0345 | 0045CD | 308 | Hurlburt Field | LF015 | Conduct LTM in accordance with the approved DD/ROD | FY30
0346 | 0045CE | 309 | Hurlburt Field | LF015 | Conduct LTM in accordance with the approved DD/ROD | FY31
0347 | 0045CF | 310 | Hurlburt Field | LF015 | Conduct LTM in accordance with the approved DD/ROD | FY32
0348 | 0045CG | 311 | Hurlburt Field | LF015 | Conduct LTM in accordance with the approved DD/ROD | FY33
0349 | 0045CH | 312 | Hurlburt Field | LF015 | Conduct LTM in accordance with the approved DD/ROD | FY34
0350 | 0045CJ | 313 | Hurlburt Field | LF015 | Conduct LTM in accordance with the approved DD/ROD | FY35
0351 | 0045CK | 314 | Hurlburt Field | LF015 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0046 |  | Hurlburt Field | LF016 | Conduct LTM
0352 | 0046CA |  | Hurlburt Field | LF016 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0353 | 0046CB | 315 | Hurlburt Field | LF016 | Conduct LTM in accordance with the approved DD/ROD | FY28
0354 | 0046CC | 316 | Hurlburt Field | LF016 | Conduct LTM in accordance with the approved DD/ROD | FY29
0355 | 0046CD | 317 | Hurlburt Field | LF016 | Conduct LTM in accordance with the approved DD/ROD | FY30
0356 | 0046CE | 318 | Hurlburt Field | LF016 | Conduct LTM in accordance with the approved DD/ROD | FY31
0357 | 0046CF | 319 | Hurlburt Field | LF016 | Conduct LTM in accordance with the approved DD/ROD | FY32
0358 | 0046CG | 320 | Hurlburt Field | LF016 | Conduct LTM in accordance with the approved DD/ROD | FY33
0359 | 0046CH | 321 | Hurlburt Field | LF016 | Conduct LTM in accordance with the approved DD/ROD | FY34
0360 | 0046CJ | 322 | Hurlburt Field | LF016 | Conduct LTM in accordance with the approved DD/ROD | FY35
0361 | 0046CK | 323 | Hurlburt Field | LF016 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0047 |  | Hurlburt Field | LF017 | Conduct LTM
0362 | 0047CA |  | Hurlburt Field | LF017 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0363 | 0047CB | 324 | Hurlburt Field | LF017 | Conduct LTM in accordance with the approved DD/ROD | FY28
0364 | 0047CC | 325 | Hurlburt Field | LF017 | Conduct LTM in accordance with the approved DD/ROD | FY29
0365 | 0047CD | 326 | Hurlburt Field | LF017 | Conduct LTM in accordance with the approved DD/ROD | FY30
0366 | 0047CE | 327 | Hurlburt Field | LF017 | Conduct LTM in accordance with the approved DD/ROD | FY31
0367 | 0047CF | 328 | Hurlburt Field | LF017 | Conduct LTM in accordance with the approved DD/ROD | FY32
0368 | 0047CG | 329 | Hurlburt Field | LF017 | Conduct LTM in accordance with the approved DD/ROD | FY33
0369 | 0047CH | 330 | Hurlburt Field | LF017 | Conduct LTM in accordance with the approved DD/ROD | FY34
0370 | 0047CJ | 331 | Hurlburt Field | LF017 | Conduct LTM in accordance with the approved DD/ROD | FY35
0371 | 0047CK | 332 | Hurlburt Field | LF017 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0048 |  | Hurlburt Field | LF018 | Conduct LTM
0372 | 0048CA |  | Hurlburt Field | LF018 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0373 | 0048CB | 333 | Hurlburt Field | LF018 | Conduct LTM in accordance with the approved DD/ROD | FY28
0374 | 0048CC | 334 | Hurlburt Field | LF018 | Conduct LTM in accordance with the approved DD/ROD | FY29
0375 | 0048CD | 335 | Hurlburt Field | LF018 | Conduct LTM in accordance with the approved DD/ROD | FY30
0376 | 0048CE | 336 | Hurlburt Field | LF018 | Conduct LTM in accordance with the approved DD/ROD | FY31
0377 | 0048CF | 337 | Hurlburt Field | LF018 | Conduct LTM in accordance with the approved DD/ROD | FY32
0378 | 0048CG | 338 | Hurlburt Field | LF018 | Conduct LTM in accordance with the approved DD/ROD | FY33
0379 | 0048CH | 339 | Hurlburt Field | LF018 | Conduct LTM in accordance with the approved DD/ROD | FY34
0380 | 0048CJ | 340 | Hurlburt Field | LF018 | Conduct LTM in accordance with the approved DD/ROD | FY35
0381 | 0048CK | 341 | Hurlburt Field | LF018 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0049 |  | Hurlburt Field | LF019 | Conduct LTM
0382 | 0049CA |  | Hurlburt Field | LF019 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0383 | 0049CB | 342 | Hurlburt Field | LF019 | Conduct LTM in accordance with the approved DD/ROD | FY28
0384 | 0049CC | 343 | Hurlburt Field | LF019 | Conduct LTM in accordance with the approved DD/ROD | FY29
0385 | 0049CD | 344 | Hurlburt Field | LF019 | Conduct LTM in accordance with the approved DD/ROD | FY30
0386 | 0049CE | 345 | Hurlburt Field | LF019 | Conduct LTM in accordance with the approved DD/ROD | FY31
0387 | 0049CF | 346 | Hurlburt Field | LF019 | Conduct LTM in accordance with the approved DD/ROD | FY32
0388 | 0049CG | 347 | Hurlburt Field | LF019 | Conduct LTM in accordance with the approved DD/ROD | FY33
0389 | 0049CH | 348 | Hurlburt Field | LF019 | Conduct LTM in accordance with the approved DD/ROD | FY34
0390 | 0049CJ | 349 | Hurlburt Field | LF019 | Conduct LTM in accordance with the approved DD/ROD | FY35
0391 | 0049CK | 350 | Hurlburt Field | LF019 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0050 |  | Hurlburt Field | LF020 | Conduct LTM
0392 | 0050CA |  | Hurlburt Field | LF020 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0393 | 0050CB | 351 | Hurlburt Field | LF020 | Conduct LTM in accordance with the approved DD/ROD | FY28
0394 | 0050CC | 352 | Hurlburt Field | LF020 | Conduct LTM in accordance with the approved DD/ROD | FY29
0395 | 0050CD | 353 | Hurlburt Field | LF020 | Conduct LTM in accordance with the approved DD/ROD | FY30
0396 | 0050CE | 354 | Hurlburt Field | LF020 | Conduct LTM in accordance with the approved DD/ROD | FY31
0397 | 0050CF | 355 | Hurlburt Field | LF020 | Conduct LTM in accordance with the approved DD/ROD | FY32
0398 | 0050CG | 356 | Hurlburt Field | LF020 | Conduct LTM in accordance with the approved DD/ROD | FY33
0399 | 0050CH | 357 | Hurlburt Field | LF020 | Conduct LTM in accordance with the approved DD/ROD | FY34
0400 | 0050CJ | 358 | Hurlburt Field | LF020 | Conduct LTM in accordance with the approved DD/ROD | FY35
0401 | 0050CK | 359 | Hurlburt Field | LF020 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0051 |  | Hurlburt Field | SS125 | Achieve Site Closeout
0402 | 0051AA | 360 | Hurlburt Field | SS125 | Achieve Remedial Action Plan | FY28
0403 | 0051AB | 361 | Hurlburt Field | SS125 | Achieve Response Complete | Optional Task
0404 | 0051AC | 362 | Hurlburt Field | SS125 | Achieve Site Closeout | Optional Task
| 0052 |  | Hurlburt Field | ST123 | Conduct LTM
0405 | 0052CA |  | Hurlburt Field | ST123 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0406 | 0052CB | 363 | Hurlburt Field | ST123 | Conduct LTM in accordance with the approved DD/ROD | FY28
0407 | 0052CC | 364 | Hurlburt Field | ST123 | Conduct LTM in accordance with the approved DD/ROD | FY29
0408 | 0052CD | 365 | Hurlburt Field | ST123 | Conduct LTM in accordance with the approved DD/ROD | FY30
0409 | 0052CE | 366 | Hurlburt Field | ST123 | Conduct LTM in accordance with the approved DD/ROD | FY31
0410 | 0052CF | 367 | Hurlburt Field | ST123 | Conduct LTM in accordance with the approved DD/ROD | FY32
0411 | 0052CG | 368 | Hurlburt Field | ST123 | Conduct LTM in accordance with the approved DD/ROD | FY33
0412 | 0052CH | 369 | Hurlburt Field | ST123 | Conduct LTM in accordance with the approved DD/ROD | FY34
0413 | 0052CJ | 370 | Hurlburt Field | ST123 | Conduct LTM in accordance with the approved DD/ROD | FY35
0414 | 0052CK | 371 | Hurlburt Field | ST123 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0053 |  | Hurlburt Field | XU002 | Achieve DD/ROD
0415 | 0053AA | 372 | Hurlburt Field | XU002 | Achieve Remedial Investigation | FY29
0416 | 0053AB | 373 | Hurlburt Field | XU002 | Achieve Feasibility Study | Optional Task
0417 | 0053AC | 374 | Hurlburt Field | XU002 | Achieve Proposed Plan | Optional Task
0418 | 0053AD | 375 | Hurlburt Field | XU002 | Achieve Record of Decision (ROD) | Optional Task
| 0054 |  | Tyndall AFB | N/A | Update Community Involvement Plan
0419 | 0054CA |  | Tyndall AFB | All Open Sites (IRP, MMRP, PFAS, etc) | Update Community Involvement Plan | Base Year (2027)
0420 | 0054CB | 376 | Tyndall AFB | All Open Sites (IRP, MMRP, PFAS, etc) | Update Community Involvement Plan | FY30
0421 | 0054CC | 377 | Tyndall AFB | All Open Sites (IRP, MMRP, PFAS, etc) | Update Community Involvement Plan | FY33
0422 | 0054CD | 378 | Tyndall AFB | All Open Sites (IRP, MMRP, PFAS, etc) | Update Community Involvement Plan | FY36
| 0055 |  | Tyndall AFB | N/A | Complete IRP Basewide Quality Program Plans (QPP)
0423 | 0055CA |  | Tyndall AFB | N/A | Complete IRP Basewide QPP | Base Year (2027)
0424 | 0055CB | 379 | Tyndall AFB | N/A | Update IRP Basewide QPP | Optional Task based on need
0425 | 0055CC | 380 | Tyndall AFB | N/A | Update IRP Basewide QPP | Optional Task based on need
| 0056 |  | Tyndall AFB | N/A | Complete MMRP Quality Program Plan (QPP)
0426 | 0056CA |  | Tyndall AFB | N/A | Complete MMRP QPP | Base Year (2027)
0427 | 0056CB | 381 | Tyndall AFB | N/A | Update MMRP QPP | Optional Task based on need
0428 | 0056CC | 382 | Tyndall AFB | N/A | Update MMRP QPP | Optional Task based on need
| 0057 |  | Tyndall AFB | N/A | Perform Well Survey, Inventory, and Condition Assessment
0429 | 0057CA | 383 | Tyndall AFB | N/A | Complete Well Survey, Inventory, and Condition Assessment | FY29
0430 | 0057CB | 384 | Tyndall AFB | N/A | Update Well Survey, Inventory, and Condition Assessment | FY33
| 0058 |  | Tyndall AFB | DA046 | Achieve Site Closeout
0431 | 0058AA | 385 | Tyndall AFB | DA046 | Achieve Confirmatory Sampling | FY28
0432 | 0058AB | 386 | Tyndall AFB | DA046 | Achieve Feasiblity Study | Optional Task
0433 | 0058AC | 387 | Tyndall AFB | DA046 | Achieve Site Closeout (No Action Proposed Plan/Record of Decision (PP/ROD)) | Optional Task
| 0059 |  | Tyndall AFB | FR038 | Conduct LTM
0434 | 0059CA |  | Tyndall AFB | FR038 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0435 | 0059CB | 388 | Tyndall AFB | FR038 | Conduct LTM in accordance with the approved DD/ROD | FY28
0436 | 0059CC | 389 | Tyndall AFB | FR038 | Conduct LTM in accordance with the approved DD/ROD | FY29
0437 | 0059CD | 390 | Tyndall AFB | FR038 | Conduct LTM in accordance with the approved DD/ROD | FY30
0438 | 0059CE | 391 | Tyndall AFB | FR038 | Conduct LTM in accordance with the approved DD/ROD | FY31
0439 | 0059CF | 392 | Tyndall AFB | FR038 | Conduct LTM in accordance with the approved DD/ROD | FY32
0440 | 0059CG | 393 | Tyndall AFB | FR038 | Conduct LTM in accordance with the approved DD/ROD | FY33
0441 | 0059CH | 394 | Tyndall AFB | FR038 | Conduct LTM in accordance with the approved DD/ROD | FY34
0442 | 0059CJ | 395 | Tyndall AFB | FR038 | Conduct LTM in accordance with the approved DD/ROD | FY35
0443 | 0059CK | 396 | Tyndall AFB | FR038 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0060 |  | Tyndall AFB | FT016 | Achieve Feasibility Study
0444 | 0060AA |  | Tyndall AFB | FT016 | Achieve Land Use Control Implementation Plan | Base Year (2027)
0445 | 0060AB | 397 | Tyndall AFB | FT016 | Achieve Post MILCON Confirmatory Sampling | Optional Task
0446 | 0060AC | 398 | Tyndall AFB | FT016 | Achieve Feasibility Study | Optional Task
0447 | 0060CA | 399 | Tyndall AFB | FT016 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY28
0448 | 0060CB | 400 | Tyndall AFB | FT016 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY29
0449 | 0060CC | 401 | Tyndall AFB | FT016 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY30
0450 | 0060CD | 402 | Tyndall AFB | FT016 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY31
0451 | 0060CE | 403 | Tyndall AFB | FT016 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY32
0452 | 0060CF | 404 | Tyndall AFB | FT016 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY33
0453 | 0060CG | 405 | Tyndall AFB | FT016 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY34
0454 | 0060CH | 406 | Tyndall AFB | FT016 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY35
0455 | 0060CJ | 407 | Tyndall AFB | FT016 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY36
| 0061 |  | Tyndall AFB | FT016 | Complete 1,4 Dioxane Step 2
0456 | 0061AA |  | Tyndall AFB | FT016 | Complete 1,4-Dioxane Step 2 Nature and Extent Determination | Base Year (2027)
| 0062 |  | Tyndall AFB | FT017 | Achieve Feasibility Study
0457 | 0062AA |  | Tyndall AFB | FT017 | Achieve Land Use Control Implementation Plan | Base Year (2027)
0458 | 0062AB | 408 | Tyndall AFB | FT017 | Achieve Post MILCON Confirmatory Sampling | Optional Task
0459 | 0062AC | 409 | Tyndall AFB | FT017 | Achieve Feasibility Study | Optional Task
0460 | 0062CA | 410 | Tyndall AFB | FT017 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY28
0461 | 0062CB | 411 | Tyndall AFB | FT017 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY29
0462 | 0062CC | 412 | Tyndall AFB | FT017 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY30
0463 | 0062CD | 413 | Tyndall AFB | FT017 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY31
0464 | 0062CE | 414 | Tyndall AFB | FT017 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY32
0465 | 0062CF | 415 | Tyndall AFB | FT017 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY33
0466 | 0062CG | 416 | Tyndall AFB | FT017 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY34
0467 | 0062CH | 417 | Tyndall AFB | FT017 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY35
0468 | 0062CJ | 418 | Tyndall AFB | FT017 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY36
| 0063 |  | Tyndall AFB | LF006 | Achieve Response Complete
0469 | 0063AA | 419 | Tyndall AFB | LF006 | Achieve Remedy in Place | FY28
0470 | 0063AB | 420 | Tyndall AFB | LF006 | Optimize the site in support of Response Complete | Optional Task
0471 | 0063AC | 421 | Tyndall AFB | LF006 | Achieve Response Complete | Optional Task
0472 | 0063CA | 422 | Tyndall AFB | LF006 | Conduct LTM in accordance with the approved DD/ROD | FY30 - Upon Completion of 0063AC (CLIN 0471)
0473 | 0063CB | 423 | Tyndall AFB | LF006 | Conduct LTM in accordance with the approved DD/ROD | FY31
0474 | 0063CC | 424 | Tyndall AFB | LF006 | Conduct LTM in accordance with the approved DD/ROD | FY32
0475 | 0063CD | 425 | Tyndall AFB | LF006 | Conduct LTM in accordance with the approved DD/ROD | FY33
0476 | 0063CE | 426 | Tyndall AFB | LF006 | Conduct LTM in accordance with the approved DD/ROD | FY34
0477 | 0063CF | 427 | Tyndall AFB | LF006 | Conduct LTM in accordance with the approved DD/ROD | FY35
0478 | 0063CG | 428 | Tyndall AFB | LF006 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0064 |  | Tyndall AFB | LF007 | Achieve Response Complete
0479 | 0064AA | 429 | Tyndall AFB | LF007 | Achieve Remedy in Place | FY28
0480 | 0064AB | 430 | Tyndall AFB | LF007 | Optimize the site in support of Response Complete | Optional Task
0481 | 0064AC | 431 | Tyndall AFB | LF007 | Achieve Response Complete | Optional Task
0482 | 0064CA | 432 | Tyndall AFB | LF007 | Conduct LTM in accordance with the approved DD/ROD | FY30 - Upon Completion of 0064AC (CLIN 0481)
0483 | 0064CB | 433 | Tyndall AFB | LF007 | Conduct LTM in accordance with the approved DD/ROD | FY31
0484 | 0064CC | 434 | Tyndall AFB | LF007 | Conduct LTM in accordance with the approved DD/ROD | FY32
0485 | 0064CD | 435 | Tyndall AFB | LF007 | Conduct LTM in accordance with the approved DD/ROD | FY33
0486 | 0064CE | 436 | Tyndall AFB | LF007 | Conduct LTM in accordance with the approved DD/ROD | FY34
0487 | 0064CF | 437 | Tyndall AFB | LF007 | Conduct LTM in accordance with the approved DD/ROD | FY35
0488 | 0064CG | 438 | Tyndall AFB | LF007 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0065 |  | Tyndall AFB | OT018 | Achieve Confirmatory Sampling
0489 | 0065AA | 439 | Tyndall AFB | OT018 | Achieve Confirmatory Sampling | FY30
| 0066 |  | Tyndall AFB | OT029 | Achieve Response Complete
0490 | 0066AA |  | Tyndall AFB | OT029 | Achieve Record of Decision | Base Year (2027)
0491 | 0066AB | 440 | Tyndall AFB | OT029 | Achieve Remedial Design and Remedial Action Work Plan | Optional Task
0492 | 0066AC | 441 | Tyndall AFB | OT029 | Achieve Remedy in Place | Optional Task
0493 | 0066AD | 442 | Tyndall AFB | OT029 | Achieve Response Complete | Optional Task
0494 | 0066CA | 443 | Tyndall AFB | OT029 | Conduct LTM in accordance with the approved DD/ROD | FY34 - Upon Completion of 0066AD (CLIN 0493)
0495 | 0066CB | 444 | Tyndall AFB | OT029 | Conduct LTM in accordance with the approved DD/ROD | FY35
0496 | 0066CC | 445 | Tyndall AFB | OT029 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0067 |  | Tyndall AFB | OW217 | Achieve Remedy in Place and RA-O
0497 | 0067AA |  | Tyndall AFB | OW217 | Achieve Land Use Control Implementation Plan | Base Year (2027)
0498 | 0067AB | 446 | Tyndall AFB | OW217 | Achieve Post MILCON Confirmatory Sampling | Optional Task
0499 | 0067AC | 447 | Tyndall AFB | OW217 | Achieve Feasibility Study | Optional Task
0500 | 0067AD | 448 | Tyndall AFB | OW217 | Achieve Proposed Plan/Record of Decision | Optional Task
0501 | 0067AE | 449 | Tyndall AFB | OW217 | Achieve Remedial Design and Remedial Action Work Plan | Optional Task
0502 | 0067AF | 450 | Tyndall AFB | OW217 | Achieve Remedy in Place | Optional Task
0503 | 0067CA | 451 | Tyndall AFB | OW217 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY28
0504 | 0067CB | 452 | Tyndall AFB | OW217 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY29
0505 | 0067CC | 453 | Tyndall AFB | OW217 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY30
0506 | 0067CD | 454 | Tyndall AFB | OW217 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY31
0507 | 0067CE | 455 | Tyndall AFB | OW217 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY32
0508 | 0067CF | 456 | Tyndall AFB | OW217 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY33
0509 | 0067CG | 457 | Tyndall AFB | OW217 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY34
0510 | 0067CH | 458 | Tyndall AFB | OW217 | Conduct RA-O in accordance with the approved DD / ROD | FY35 - Upon completion of 0067AF (CLIN 0502)
0511 | 0067CJ | 459 | Tyndall AFB | OW217 | Conduct RA-O in accordance with the approved DD / ROD | FY36
| 0068 |  | Tyndall AFB | OW582 | Achieve Remedy in Place and RA-O
0512 | 0068AA | 460 | Tyndall AFB | OW582 | Achieve Remedial Design and Remedial Action Work Plan | FY29
0513 | 0068AB | 461 | Tyndall AFB | OW582 | Achieve Remedy in Place | Optional Task
0514 | 0068CA | 462 | Tyndall AFB | OW582 | Conduct RAO in accordance with the approved DD / ROD and evaluate performance model | FY33 - Upon Completion of 0068AB (CLIN 0513)
0515 | 0068CB | 463 | Tyndall AFB | OW582 | Conduct RAO in accordance with the approved DD / ROD and evaluate performance model | FY34
0516 | 0068CC | 464 | Tyndall AFB | OW582 | Conduct RAO in accordance with the approved DD / ROD and evaluate performance model | FY35
0517 | 0068CD | 465 | Tyndall AFB | OW582 | Conduct RAO in accordance with the approved DD / ROD and evaluate performance model | FY36
| 0069 |  | Tyndall AFB | SR169 | Achieve Site Closeout
0518 | 0069AA | 466 | Tyndall AFB | SR169 | Achieve Site Closeout | FY29
| 0070 |  | Tyndall AFB | SR170 | Achieve DD/ROD
0519 | 0070AA |  | Tyndall AFB | SR170 | Achieve Record of Decision | Base Year (2027)
| 0071 |  | Tyndall AFB | SR170A | Conduct LTM
0520 | 0071CA | 467 | Tyndall AFB | SR170A | Conduct LTM in accordance with the approved DD / ROD | FY29
0521 | 0071CB | 468 | Tyndall AFB | SR170A | Conduct LTM in accordance with the approved DD / ROD | FY30
0522 | 0071CC | 469 | Tyndall AFB | SR170A | Conduct LTM in accordance with the approved DD / ROD | FY31
0523 | 0071CD | 470 | Tyndall AFB | SR170A | Conduct LTM in accordance with the approved DD / ROD | FY32
0524 | 0071CE | 471 | Tyndall AFB | SR170A | Conduct LTM in accordance with the approved DD / ROD | FY33
0525 | 0071CF | 472 | Tyndall AFB | SR170A | Conduct LTM in accordance with the approved DD / ROD | FY34
0526 | 0071CG | 473 | Tyndall AFB | SR170A | Conduct LTM in accordance with the approved DD / ROD | FY35
0527 | 0071CH | 474 | Tyndall AFB | SR170A | Conduct LTM in accordance with the approved DD / ROD | FY36
| 0072 |  | Tyndall AFB | SS015 | Achieve Remedy in Place and RA-O
0528 | 0072AA |  | Tyndall AFB | SS015 | Achieve Land Use Control Implementation Plan | Base Year (2027)
0529 | 0072AB | 475 | Tyndall AFB | SS015 | Achieve Post MILCON Confirmatory Sampling | Optional Task based on need
0530 | 0072AC | 476 | Tyndall AFB | SS015 | Achieve Feasibility Study | Optional Task based on need
0531 | 0072AD | 477 | Tyndall AFB | SS015 | Achieve Proposed Plan/Record of Decision (PP/ROD) | Optional Task based on need
0532 | 0072AE | 478 | Tyndall AFB | SS015 | Achieve Remedial Design and Remedial Action Work Plan | Optional Task based on need
0533 | 0072AF | 479 | Tyndall AFB | SS015 | Achieve Remedy in Place | Optional Task based on need
0534 | 0072CA | 480 | Tyndall AFB | SS015 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY28
0535 | 0072CB | 481 | Tyndall AFB | SS015 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY29
0536 | 0072CC | 482 | Tyndall AFB | SS015 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY30
0537 | 0072CD | 483 | Tyndall AFB | SS015 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY31
0538 | 0072CE | 484 | Tyndall AFB | SS015 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY32
0539 | 0072CF | 485 | Tyndall AFB | SS015 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY33
0540 | 0072CG | 486 | Tyndall AFB | SS015 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY34
0541 | 0072CH | 487 | Tyndall AFB | SS015 | Conduct RA-O in accordance with the approved DD / ROD | FY35 - Upon completion of 0072AF (CLIN 0533)
0542 | 0072CJ | 488 | Tyndall AFB | SS015 | Conduct RA-O in accordance with the approved DD / ROD | FY36
| 0073 |  | Tyndall AFB | SS026 | Achieve Remedy in Place and RA-O
0543 | 0073AA |  | Tyndall AFB | SS026 | Achieve Land Use Control Implementation Plan | Base Year (2027)
0544 | 0073AB | 489 | Tyndall AFB | SS026 | Achieve Post MILCON Confirmatory Sampling | Optional Task based on need
0545 | 0073AC | 490 | Tyndall AFB | SS026 | Achieve Feasibility Study | Optional Task based on need
0546 | 0073AD | 500 | Tyndall AFB | SS026 | AchieveProposed Plan/Record of Decision (PP/ROD) | Optional Task based on need
0547 | 0073AE | 501 | Tyndall AFB | SS026 | Achieve Remedial Design and Remedial Action Work Plan | Optional Task based on need
0548 | 0073AF | 502 | Tyndall AFB | SS026 | Achieve Remedy in Place | Optional Task based on need
0549 | 0073CA | 503 | Tyndall AFB | SS026 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY28
0550 | 0073CB | 504 | Tyndall AFB | SS026 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY29
0551 | 0073CC | 505 | Tyndall AFB | SS026 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY30
0552 | 0073CD | 506 | Tyndall AFB | SS026 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY31
0553 | 0073CE | 507 | Tyndall AFB | SS026 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY32
0554 | 0073CF | 508 | Tyndall AFB | SS026 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY33
0555 | 0073CG | 509 | Tyndall AFB | SS026 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY34
0556 | 0073CH | 510 | Tyndall AFB | SS026 | Conduct RA-O in accordance with the approved DD / ROD | FY35 - Upon completion of 0073AF (CLIN 0548)
0557 | 0073CJ | 511 | Tyndall AFB | SS026 | Conduct RA-O in accordance with the approved DD / ROD | FY36
| 0074 |  | Tyndall AFB | TA523 | Conduct LTM
0558 | 0074CA |  | Tyndall AFB | TA523 | Conduct LTM in accordance with the approved DD/ROD | Base Year (2027)
0559 | 0074CB | 512 | Tyndall AFB | TA523 | Conduct LTM in accordance with the approved DD/ROD | FY28
0560 | 0074CC | 513 | Tyndall AFB | TA523 | Conduct LTM in accordance with the approved DD/ROD | FY29
0561 | 0074CD | 514 | Tyndall AFB | TA523 | Conduct LTM in accordance with the approved DD/ROD | FY30
0562 | 0074CE | 515 | Tyndall AFB | TA523 | Conduct LTM in accordance with the approved DD/ROD | FY31
0563 | 0074CF | 516 | Tyndall AFB | TA523 | Conduct LTM in accordance with the approved DD/ROD | FY32
0564 | 0074CG | 517 | Tyndall AFB | TA523 | Conduct LTM in accordance with the approved DD/ROD | FY33
0565 | 0074CH | 518 | Tyndall AFB | TA523 | Conduct LTM in accordance with the approved DD/ROD | FY34
0566 | 0074CJ | 519 | Tyndall AFB | TA523 | Conduct LTM in accordance with the approved DD/ROD | FY35
0567 | 0074CK | 520 | Tyndall AFB | TA523 | Conduct LTM in accordance with the approved DD/ROD | FY36
| 0075 |  | Tyndall AFB | TS183 | RA-O with Optimization
0568 | 0075AA | 521 | Tyndall AFB | TS183 | Prepare Performance Model in year 2 and achieve the performance goals per the Performance Model and provide Performance Evaluation Report years 3 and 4 | FY28
0569 | 0075AB | 522 | Tyndall AFB | TS183 | Achieve the performance goals per the performance model and provide Performance Evaluation Report years 5, 6, and 7 | Optional Task
0570 | 0075AC | 523 | Tyndall AFB | TS183 | Achieve the performance goals per the performance model and provide Performance Evaluation Report years 8, and 9, develop an Optimization Summary and Forecasting Report in year 8 and provide final performance goal in year 10 | Optional Task
0571 | 0075CA | 524 | Tyndall AFB | TS183 | Conduct RA-O in accordance with the approved DD / ROD | FY28
0572 | 0075CB | 525 | Tyndall AFB | TS183 | Conduct RA-O in accordance with the approved DD / ROD | FY29
0573 | 0075CC | 526 | Tyndall AFB | TS183 | Conduct RA-O in accordance with the approved DD / ROD | FY30
0574 | 0075CD | 527 | Tyndall AFB | TS183 | Conduct RA-O in accordance with the approved DD / ROD | FY31
0575 | 0075CE | 528 | Tyndall AFB | TS183 | Conduct RA-O in accordance with the approved DD / ROD | FY32
0576 | 0075CF | 529 | Tyndall AFB | TS183 | Conduct RA-O in accordance with the approved DD / ROD | FY33
0577 | 0075CG | 530 | Tyndall AFB | TS183 | Conduct RA-O in accordance with the approved DD / ROD | FY34
0578 | 0075CH | 531 | Tyndall AFB | TS183 | Conduct RA-O in accordance with the approved DD / ROD | FY35
0579 | 0075CJ | 532 | Tyndall AFB | TS183 | Conduct RA-O in accordance with the approved DD / ROD | FY36
| 0076 |  | Tyndall AFB | TU204 | Achieve Site Closeout
0580 | 0076AA | 533 | Tyndall AFB | TU204 | Optimize the site in support of Site Closeout | FY29
0581 | 0076AB | 534 | Tyndall AFB | TU204 | Achieve Response Complete | Optional Task based on need
0582 | 0076AC | 535 | Tyndall AFB | TU204 | Achieve Site Closeout | Optional Task based on need
| 0077 |  | Tyndall AFB | TU205 | Achieve Remedy in Place and RA-O
0583 | 0077AA |  | Tyndall AFB | TU205 | Achieve Land Use Control Implementation Plan | Base Year (2027)
0584 | 0077AB | 536 | Tyndall AFB | TU205 | Achieve Post MILCON Confirmatory Sampling | Optional Task based on need
0585 | 0077AC | 537 | Tyndall AFB | TU205 | Achieve Feasibility Study | Optional Task based on need
0586 | 0077AD | 538 | Tyndall AFB | TU205 | Achieve Proposed Plan/Record of Decision (PP/ROD) | Optional Task based on need
0587 | 0077AE | 539 | Tyndall AFB | TU205 | Achieve Remedial Design and Remedial Action Work Plan | Optional Task based on need
0588 | 0077AF | 540 | Tyndall AFB | TU205 | Achieve Remedy in Place | Optional Task based on need
0589 | 0077CA | 541 | Tyndall AFB | TU205 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY28
0590 | 0077CB | 542 | Tyndall AFB | TU205 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY29
0591 | 0077CC | 543 | Tyndall AFB | TU205 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY30
0592 | 0077CD | 544 | Tyndall AFB | TU205 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY31
0593 | 0077CE | 545 | Tyndall AFB | TU205 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY32
0594 | 0077CF | 546 | Tyndall AFB | TU205 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY33
0595 | 0077CG | 547 | Tyndall AFB | TU205 | Conduct RA-O in accordance with the approved Interim DD / ROD | FY34
0596 | 0077CH | 548 | Tyndall AFB | TU205 | Conduct RA-O in accordance with the approved DD / ROD | FY35
0597 | 0077CJ | 549 | Tyndall AFB | TU205 | Conduct RA-O in accordance with the approved DD / ROD | FY36
| 0078 |  | Tyndall AFB | TU233 | Achieve Site Closeout
0598 | 0078AA |  | Tyndall AFB | TU233 | Corrective Measures Implementation Plan (UFP-QAPP PARM Work Plan) | Base Year (2027)
0599 | 0078AB | 550 | Tyndall AFB | TU233 | Construction Completion (Achieve PARM) | Optional Task based on need
0600 | 0078AC | 551 | Tyndall AFB | TU233 | Achieve Response Complete | Optional Task based on need
0601 | 0078AD | 552 | Tyndall AFB | TU233 | Achieve Site Closeout (SRCR and Well Abandonment Report) | Optional Task based on need
*1 The Projected/Estimated award timing designation in column E, F, & G indicate projected/estimated award timing each of the associated AFCEC Sub-CLINs will be funded and exercised. The "exercise year" is included for planning purposes only and is not intended to indicate a commitment by the Government to fund and exercise an AFCEC Sub-CLIN in a specific year of the contract. Award of all AFCEC Sub-CLINs will be made pending availability of funds and if bona fide need is determined by the Government. Limitations on funding availability may necessitate the Government to prioritize AFCEC Sub-CLIN award based on funding, regulatory requirements, and other bonafide need requirements. Meeting annual award dates for compliance AFCEC Sub-CLINs is necessary to maintain conformity with AF legal obligations, including Records of Decision (RODs), permits, and other agreements. These dates should not be confused with the time to obtain final regulatory approval of the reports associated with these annually funded events. Final reports generally take more than 12 months so these events, while funded annually, are non-severable in nature.