## Cover
Domestic Private Sector Workload Estimate
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”
CMAV Workload FY26 Q3 – FY27 Q2 as of 03 JUNE 2026
Industry Version
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”

## Notes
Data contained in this report reflects the Navy program of record as of 03 JUNE 2026.
This report is provided to our CONUS industry partners for information and planning purposes only. The information provided reflects a broad overview of current maintenance schedules and is subject to change based on operational commitments. It does not constitute a request for information or proposals, nor is it a commitment to contract work in accordance with this plan.
The next bi-monthly CMAV workload projections are targeted for release no later than 31 AUGUST 2026.
Availability duration and schedule review, tailored acquisition strategies and ongoing budget negotiations may refine out-year projections.
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## MARMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
LSD 44 | GUNSTON HALL | Little Creek | CMAV (A) | ACTIVE | 2025-12-15 | 2026-07-31 | 229
LCU 1654 | LCU 1654 | Little Creek | CMAV (A) | ACTIVE | 2026-03-01 | 2026-07-01 | 123
LPD 29 | RICHARD M MCCOOL | Norfolk | CMAV (A) | ACTIVE | 2026-03-30 | 2026-04-17 | 19
CG 64 | GETTYSBURG | Norfolk | CMAV (A) | ACTIVE | 2026-03-30 | 2026-05-08 | 40
LPD 24 | ARLINGTON | Norfolk | CMAV (A) | ACTIVE | 2026-04-13 | 2026-06-05 | 54
DDG 95 | JAMES E WILLIAMS | Norfolk | CMAV (A) | ACTIVE | 2026-04-20 | 2026-05-29 | 40
NS 7901 | NARRAGANSETT | Little Creek | CMAV (A) | ACTIVE | 2026-05-04 | 2026-06-19 | 47
DDG 124 | HARVEY C BARNUM JR | Norfolk | CMAV (A) | ACTIVE | 2026-05-04 | 2026-06-05 | 33
LSD 46 | TORTUGA | Little Creek | CMAV (A) | ACTIVE | 2026-05-11 | 2026-07-31 | 82
DDG 72 | MAHAN | Norfolk | CMAV (A) | ACTIVE | 2026-05-18 | 2026-07-02 | 46
IX 537 | PREVAIL | Norfolk | CMAV (A) | ACTIVE | 2026-07-06 | 2026-08-21 | 47
LHD 1 | WASP | Norfolk | CMAV (A) | ACTIVE | 2026-07-13 | 2026-08-21 | 40
LPD 28 | FORT LAUDERDALE | Norfolk | CMAV (A) | ACTIVE | 2026-07-14 | 2026-08-21 | 39
DDG 94 | NITZE | Norfolk | CMAV (A) | ACTIVE | 2026-07-20 | 2026-08-28 | 40
DDG 103 | TRUXTUN | Norfolk | CMAV (A) | ACTIVE | 2026-07-27 | 2026-08-21 | 26
DDG 74 | MCFAUL | Norfolk | CMAV (A) | ACTIVE | 2026-07-27 | 2026-09-04 | 40
LHD 3 | KEARSARGE | Norfolk | CMAV (A) | ACTIVE | 2026-08-03 | 2026-08-21 | 19
CG 64 | GETTYSBURG | Norfolk | CMAV (A) | ACTIVE | 2026-08-03 | 2026-09-25 | 54
LPD 19 | MESA VERDE | Norfolk | CMAV (A) | ACTIVE | 2026-08-10 | 2026-12-18 | 131
DDG 72 | MAHAN | Norfolk | CMAV (A) | ACTIVE | 2026-08-17 | 2026-09-27 | 42
DDG 58 | LABOON | Norfolk | CMAV (A) | ACTIVE | 2026-08-24 | 2026-10-02 | 40
LHD 7 | IWO JIMA | Norfolk | CMAV (A) | ACTIVE | 2026-08-24 | 2026-11-01 | 70
DDG 124 | HARVEY C BARNUM JR | Norfolk | CMAV (A) | ACTIVE | 2026-08-31 | 2026-10-12 | 43
DDG 95 | JAMES E WILLIAMS | Norfolk | CMAV (A) | ACTIVE | 2026-09-08 | 2026-10-09 | 32
LPD 24 | ARLINGTON | Norfolk | CMAV (A) | ACTIVE | 2026-09-08 | 2026-10-30 | 53
DDG 55 | STOUT | Norfolk | CMAV (A) | ACTIVE | 2026-09-14 | 2026-10-09 | 26
LHD 3 | KEARSARGE | Norfolk | CMAV (A) | ACTIVE | 2026-09-14 | 2026-10-30 | 47
TR 8202 | HUNTER | Little Creek | CMAV (A) | ACTIVE | 2026-09-21 | 2026-11-04 | 45
DDG 78 | PORTER | Norfolk | CMAV (A) | ACTIVE | 2026-10-05 | 2026-11-13 | 40
LPD 17 | SAN ANTONIO | Norfolk | CMAV (A) | ACTIVE | 2026-10-05 | 2026-11-13 | 40
DDG 94 | NITZE | Norfolk | CMAV (A) | ACTIVE | 2026-10-13 | 2027-01-08 | 88
LHD 5 | BATAAN | Norfolk | CMAV (A) | ACTIVE | 2026-10-26 | 2026-12-18 | 54
LHD 1 | WASP | Norfolk | CMAV (A) | ACTIVE | 2026-11-23 | 2027-01-08 | 47
LPD 17 | SAN ANTONIO | Norfolk | CMAV (A) | ACTIVE | 2026-11-23 | 2027-01-18 | 57
LPD 21 | NEW YORK | Norfolk | CMAV (A) | ACTIVE | 2026-11-23 | 2027-02-19 | 89
DDG 107 | GRAVELY | Norfolk | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-22 | 54
DDG 66 | GONZALEZ | Norfolk | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-22 | 54
DDG 95 | JAMES E WILLIAMS | Norfolk | CMAV (A) | ACTIVE | 2027-03-01 | 2027-04-09 | 40
LPD 28 | FORT LAUDERDALE | Norfolk | CMAV (A) | ACTIVE | 2027-03-15 | 2027-04-23 | 40
LSD 46 | TORTUGA | Little Creek | CMAV (A) | ACTIVE | 2027-03-29 | 2027-04-23 | 26
LHD 3 | KEARSARGE | Norfolk | CMAV (A) | ACTIVE | 2027-03-29 | 2027-04-23 | 26
LPD 24 | ARLINGTON | Norfolk | CMAV (A) | ACTIVE | 2027-03-29 | 2027-04-23 | 26
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## SERMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
LCS 27 | NANTUCKET | Mayport | CMAV (A) | COMPLETED | 2025-07-28 | 2026-05-05 | 282
LCS 17 | INDIANAPOLIS | Mayport | CMAV (A) | ACTIVE | 2026-01-05 | 2026-06-05 | 152
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2026-03-13 | 2026-04-03 | 22
DDG 87 | MASON | Mayport | CMAV (A) | ACTIVE | 2026-03-13 | 2026-04-03 | 22
DDG 122 | JOHN BASILONE | Mayport | CMAV (A) | ACTIVE | 2026-04-06 | 2026-07-03 | 89
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2026-04-27 | 2026-06-04 | 39
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2026-04-27 | 2026-06-12 | 47
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2026-05-11 | 2026-06-19 | 40
LCS 17 | INDIANAPOLIS | Mayport | CMAV (A) | ACTIVE | 2026-05-18 | 2026-06-12 | 26
DDG 61 | RAMAGE | Mayport | CMAV (A) | ACTIVE | 2026-05-18 | 2026-06-12 | 26
DDG 81 | WINSTON S CHURCHILL | Mayport | CMAV (A) | ACTIVE | 2026-05-18 | 2026-07-10 | 54
LCS 19 | ST LOUIS | Mayport | CMAV (A) | ACTIVE | 2026-06-15 | 2026-07-24 | 40
LCS 31 | CLEVELAND | Mayport | CMAV (A) | ACTIVE | 2026-06-15 | 2026-09-11 | 89
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2026-07-13 | 2026-07-31 | 19
DDG 99 | FARRAGUT | Mayport | CMAV (A) | ACTIVE | 2026-07-13 | 2026-08-11 | 30
DDG 109 | JASON DUNHAM | Mayport | CMAV (A) | ACTIVE | 2026-07-29 | 2026-08-20 | 23
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2026-08-03 | 2026-08-21 | 19
DDG 116 | THOMAS HUDNER | Mayport | CMAV (A) | ACTIVE | 2026-08-03 | 2026-08-30 | 28
LCS 21 | MINNEAPOLIS-SAINT PAUL | Mayport | CMAV (A) | ACTIVE | 2026-08-03 | 2026-09-11 | 40
LCS 23 | COOPERSTOWN | Mayport | CMAV (A) | ACTIVE | 2026-08-10 | 2026-09-18 | 40
DDG 119 | DELBERT D BLACK | Mayport | CMAV (A) | ACTIVE | 2026-08-17 | 2026-09-25 | 40
LCS 29 | BELOIT | Mayport | CMAV (A) | ACTIVE | 2026-09-07 | 2027-04-16 | 222
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2026-09-14 | 2026-10-16 | 33
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2026-09-14 | 2026-10-23 | 40
LCS 19 | ST LOUIS | Mayport | CMAV (A) | ACTIVE | 2026-10-05 | 2026-11-13 | 40
DDG 64 | CARNEY | Mayport | CMAV (A) | ACTIVE | 2026-10-12 | 2026-11-13 | 33
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2026-10-12 | 2026-11-13 | 33
DDG 61 | RAMAGE | Mayport | CMAV (A) | ACTIVE | 2026-10-12 | 2026-11-13 | 33
LCS 15 | BILLINGS | Mayport | CMAV (A) | ACTIVE | 2026-10-13 | 2026-11-20 | 39
LCS 23 | COOPERSTOWN | Mayport | CMAV (A) | ACTIVE | 2026-10-19 | 2026-11-27 | 40
DDG 122 | JOHN BASILONE | Mayport | CMAV (A) | ACTIVE | 2026-10-19 | 2026-12-11 | 54
DDG 99 | FARRAGUT | Mayport | CMAV (A) | ACTIVE | 2026-11-16 | 2027-01-08 | 54
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2026-11-16 | 2027-01-10 | 56
DDG 87 | MASON | Mayport | CMAV (A) | ACTIVE | 2026-11-16 | 2027-01-15 | 61
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2026-11-30 | 2026-12-18 | 19
DDG 61 | RAMAGE | Mayport | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-08 | 40
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-08 | 40
DDG 64 | CARNEY | Mayport | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-08 | 40
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2027-01-19 | 2027-03-02 | 43
LCS 21 | MINNEAPOLIS-SAINT PAUL | Mayport | CMAV (A) | ACTIVE | 2027-01-19 | 2027-03-05 | 46
DDG 122 | JOHN BASILONE | Mayport | CMAV (A) | ACTIVE | 2027-02-22 | 2027-03-12 | 19
DDG 99 | FARRAGUT | Mayport | CMAV (A) | ACTIVE | 2027-02-22 | 2027-03-12 | 19
DDG 64 | CARNEY | Mayport | CMAV (A) | ACTIVE | 2027-02-22 | 2027-03-12 | 19
DDG 61 | RAMAGE | Mayport | CMAV (A) | ACTIVE | 2027-02-22 | 2027-03-19 | 26
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2027-02-22 | 2027-03-19 | 26
LCS 17 | INDIANAPOLIS | Mayport | CMAV (A) | ACTIVE | 2027-02-22 | 2027-04-16 | 54
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## SWRMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
LHD 2 | ESSEX | San Diego | CMAV (A) | ACTIVE | 2026-02-23 | 2026-04-03 | 40
LCS 28 | SAVANNAH | San Diego | CMAV (A) | ACTIVE | 2026-02-23 | 2026-04-03 | 40
LHD 8 | MAKIN ISLAND | San Diego | CMAV (A) | ACTIVE | 2026-03-02 | 2026-04-10 | 40
DDG 123 | LENAH H SUTCLIFFE HIGBEE | San Diego | CMAV (A) | ACTIVE | 2026-03-02 | 2026-04-10 | 40
LCS 20 | CINCINNATI | San Diego | CMAV (A) | ACTIVE | 2026-03-09 | 2026-05-07 | 60
LCS 6 | JACKSON | San Diego | CMAV (A) | ACTIVE | 2026-03-23 | 2026-05-15 | 54
LCS 14 | MANCHESTER | San Diego | CMAV (A) | ACTIVE | 2026-03-26 | 2026-05-01 | 37
LCS 24 | OAKLAND | San Diego | CMAV (A) | ACTIVE | 2026-04-13 | 2026-05-22 | 40
DDG 106 | STOCKDALE | San Diego | CMAV (A) | ACTIVE | 2026-04-13 | 2026-05-22 | 40
LCS 22 | KANSAS CITY | San Diego | CMAV (A) | ACTIVE | 2026-04-20 | 2026-05-17 | 28
LCS 36 | KINGSVILLE | San Diego | CMAV (A) | ACTIVE | 2026-04-27 | 2026-05-29 | 33
LCS 12 | OMAHA | San Diego | CMAV (A) | ACTIVE | 2026-05-11 | 2026-06-23 | 44
LCS 3 | FORT WORTH | San Diego | CMAV (A) | ACTIVE | 2026-05-11 | 2026-07-24 | 75
DDG 60 | PAUL HAMILTON | San Diego | CMAV (A) | ACTIVE | 2026-05-18 | 2026-06-15 | 29
DDG 93 | CHUNG-HOON | San Diego | CMAV (A) | ACTIVE | 2026-05-18 | 2026-06-26 | 40
LSD 42 | GERMANTOWN | San Diego | CMAV (A) | ACTIVE | 2026-05-26 | 2026-09-18 | 116
DDG 125 | JACK H LUCAS | San Diego | CMAV (A) | ACTIVE | 2026-05-29 | 2026-07-17 | 50
LCS 26 | MOBILE | San Diego | CMAV (A) | ACTIVE | 2026-06-01 | 2026-07-12 | 42
DDG 90 | CHAFEE | San Diego | CMAV (A) | ACTIVE | 2026-06-15 | 2026-08-03 | 50
DDG 92 | MOMSEN | San Diego | CMAV (A) | ACTIVE | 2026-06-16 | 2026-07-19 | 34
LCS 8 | MONTGOMERY | San Diego | CMAV (A) | ACTIVE | 2026-06-22 | 2026-07-31 | 40
LCS 18 | CHARLESTON | San Diego | CMAV (A) | ACTIVE | 2026-06-29 | 2026-08-21 | 54
CG 70 | LAKE ERIE | San Diego | CMAV (A) | ACTIVE | 2026-06-29 | 2026-09-23 | 87
LCS 6 | JACKSON | San Diego | CMAV (A) | ACTIVE | 2026-07-06 | 2026-08-14 | 40
DDG 62 | FITZGERALD | San Diego | CMAV (A) | ACTIVE | 2026-07-13 | 2026-08-21 | 40
DDG 104 | STERETT | San Diego | CMAV (A) | ACTIVE | 2026-08-03 | 2026-09-11 | 40
LCS 34 | AUGUSTA | San Diego | CMAV (A) | ACTIVE | 2026-08-03 | 2026-09-11 | 40
DDG 59 | RUSSELL | San Diego | CMAV (A) | ACTIVE | 2026-08-03 | 2026-09-11 | 40
LSD 48 | ASHLAND | San Diego | CMAV (A) | ACTIVE | 2026-08-10 | 2026-09-11 | 33
DDG 60 | PAUL HAMILTON | San Diego | CMAV (A) | ACTIVE | 2026-08-10 | 2026-09-21 | 43
DDG 111 | SPRUANCE | San Diego | CMAV (A) | ACTIVE | 2026-08-17 | 2026-09-25 | 40
CG 65 | CHOSIN | San Diego | CMAV (A) | ACTIVE | 2026-08-20 | 2026-09-30 | 42
LHD 8 | MAKIN ISLAND | San Diego | CMAV (A) | ACTIVE | 2026-08-31 | 2026-09-25 | 26
LPD 23 | ANCHORAGE | San Diego | CMAV (A) | ACTIVE | 2026-08-31 | 2026-09-25 | 26
LPD 26 | JOHN P MURTHA | San Diego | CMAV (A) | ACTIVE | 2026-09-01 | 2026-09-23 | 23
DDG 63 | STETHEM | San Diego | CMAV (A) | ACTIVE | 2026-09-07 | 2026-10-15 | 39
LCS 24 | OAKLAND | San Diego | CMAV (A) | ACTIVE | 2026-09-21 | 2026-10-30 | 40
LCS 20 | CINCINNATI | San Diego | CMAV (A) | ACTIVE | 2026-09-21 | 2026-10-30 | 40
DDG 91 | PINCKNEY | San Diego | CMAV (A) | ACTIVE | 2026-10-01 | 2026-10-21 | 21
DDG 60 | PAUL HAMILTON | San Diego | CMAV (A) | ACTIVE | 2026-10-05 | 2026-11-13 | 40
DDG 54 | CURTIS WILBUR | San Diego | CMAV (A) | ACTIVE | 2026-10-05 | 2026-11-13 | 40
DDG 1000 | ZUMWALT | San Diego | CMAV (A) | ACTIVE | 2026-10-11 | 2026-12-31 | 82
LCS 38 | PIERRE | San Diego | CMAV (A) | ACTIVE | 2026-10-12 | 2026-11-20 | 40
CG 62 | ROBERT SMALLS | San Diego | CMAV (A) | ACTIVE | 2026-10-12 | 2026-11-20 | 40
CG 71 | CAPE ST GEORGE | San Diego | CMAV (A) | ACTIVE | 2026-10-12 | 2026-12-11 | 61
DDG 90 | CHAFEE | San Diego | CMAV (A) | ACTIVE | 2026-11-02 | 2026-12-11 | 40
DDG 111 | SPRUANCE | San Diego | CMAV (A) | ACTIVE | 2026-11-09 | 2027-01-08 | 61
LCS 14 | MANCHESTER | San Diego | CMAV (A) | ACTIVE | 2026-11-17 | 2027-01-08 | 53
LCS 26 | MOBILE | San Diego | CMAV (A) | ACTIVE | 2026-11-23 | 2027-01-08 | 47
CG 59 | PRINCETON | San Diego | CMAV (A) | ACTIVE | 2026-11-23 | 2027-02-12 | 82
LCS 12 | OMAHA | San Diego | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-08 | 40
DDG 104 | STERETT | San Diego | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-22 | 54
DDG 59 | RUSSELL | San Diego | CMAV (A) | ACTIVE | 2026-12-07 | 2027-01-15 | 40
DDG 97 | HALSEY | San Diego | CMAV (A) | ACTIVE | 2027-01-08 | 2027-02-18 | 42
LCS 8 | MONTGOMERY | San Diego | CMAV (A) | ACTIVE | 2027-01-08 | 2027-03-19 | 71
LSD 45 | COMSTOCK | San Diego | CMAV (A) | ACTIVE | 2027-01-11 | 2027-02-26 | 47
LHD 4 | BOXER | San Diego | CMAV (A) | ACTIVE | 2027-01-11 | 2027-02-26 | 47
LSD 48 | ASHLAND | San Diego | CMAV (A) | ACTIVE | 2027-01-18 | 2027-05-08 | 111
LCS 20 | CINCINNATI | San Diego | CMAV (A) | ACTIVE | 2027-01-25 | 2027-03-07 | 42
LCS 36 | KINGSVILLE | San Diego | CMAV (A) | ACTIVE | 2027-01-25 | 2027-03-19 | 54
LPD 27 | PORTLAND | San Diego | CMAV (A) | ACTIVE | 2027-02-08 | 2027-03-26 | 47
CG 71 | CAPE ST GEORGE | San Diego | CMAV (A) | ACTIVE | 2027-02-22 | 2027-03-26 | 33
DDG 125 | JACK H LUCAS | San Diego | CMAV (A) | ACTIVE | 2027-02-22 | 2027-04-02 | 40
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## NWRMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
DDG 53 | JOHN PAUL JONES | Everett | CMAV (A) | ACTIVE | 2026-03-09 | 2026-04-08 | 31
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2026-03-30 | 2026-05-08 | 40
DDG 56 | JOHN S MCCAIN | Everett | CMAV (A) | ACTIVE | 2026-05-04 | 2026-07-03 | 61
DDG 52 | BARRY | Everett | CMAV (A) | ACTIVE | 2026-05-18 | 2026-06-26 | 40
DDG 53 | JOHN PAUL JONES | Everett | CMAV (A) | ACTIVE | 2026-05-19 | 2026-06-05 | 18
DDG 102 | SAMPSON | Everett | CMAV (A) | ACTIVE | 2026-06-01 | 2026-06-26 | 26
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2026-08-03 | 2026-09-11 | 40
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2026-10-19 | 2026-11-27 | 40
DDG 56 | JOHN S MCCAIN | Everett | CMAV (A) | ACTIVE | 2026-11-16 | 2026-12-30 | 45
DDG 52 | BARRY | Everett | CMAV (A) | ACTIVE | 2026-11-23 | 2027-01-08 | 47
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2027-01-11 | 2027-02-19 | 40
LCS 10 | GABRIELLE GIFFORDS | SEATTLE | CMAV (A) | ACTIVE | 2027-03-11 | 2027-04-27 | 48
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## HRMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
DDG 118 | DANIEL INOUYE | Pearl Harbor | CMAV (A) | ACTIVE | 2026-03-09 | 2026-04-17 | 40
DDG 70 | HOPPER | Pearl Harbor | CMAV (A) | ACTIVE | 2026-03-16 | 2026-04-24 | 40
DDG 73 | DECATUR | Honolulu | CMAV (A) | ACTIVE | 2026-05-26 | 2026-07-03 | 39
DDG 108 | WAYNE E MEYER | Pearl Harbor | CMAV (A) | ACTIVE | 2026-05-26 | 2026-06-25 | 31
DDG 110 | WILLIAM P LAWRENCE | Pearl Harbor | CMAV (A) | ACTIVE | 2026-06-08 | 2026-07-17 | 40
CG 67 | SHILOH | Pearl Harbor | CMAV (A) | ACTIVE | 2026-06-22 | 2026-09-23 | 94
DDG 121 | FRANK E PETERSEN JR | Pearl Harbor | CMAV (A) | ACTIVE | 2026-08-03 | 2026-09-11 | 40
DDG 73 | DECATUR | Honolulu | CMAV (A) | ACTIVE | 2026-08-10 | 2026-09-18 | 40
DDG 112 | MICHAEL MURPHY | Pearl Harbor | CMAV (A) | ACTIVE | 2026-08-10 | 2026-09-18 | 40
DDG 120 | CARL M LEVIN | Pearl Harbor | CMAV (A) | ACTIVE | 2026-08-10 | 2026-09-25 | 47
DDG 118 | DANIEL INOUYE | Pearl Harbor | CMAV (A) | ACTIVE | 2026-08-31 | 2026-09-25 | 26
DDG 70 | HOPPER | Pearl Harbor | CMAV (A) | ACTIVE | 2026-09-14 | 2026-10-23 | 40
DDG 112 | MICHAEL MURPHY | Pearl Harbor | CMAV (A) | ACTIVE | 2026-10-19 | 2026-12-04 | 47
DDG 118 | DANIEL INOUYE | Pearl Harbor | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-22 | 54
DDG 108 | WAYNE E MEYER | Pearl Harbor | CMAV (A) | ACTIVE | 2027-01-19 | 2027-02-05 | 18
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”