# Regional Kitchen Materials Index

This index contains document title, date or version, status, and electronic format of  planning products for the Regional Kitchen and Finishing Kitchen

| Working area | Files provided | Identified gaps |
| --- | --- | --- |
| Menu, recipe, and production | MENU-01_RK_Five_Week_Cycle_Menu.xlsx MENU-02_RK_Menu_Recipe_Production_Manager_Workbook.xlsx MENU-03_RK_Standardized_Recipe_Database.xlsx PROC-01_RK_Recipe_Ingredient_Master.xlsx | Confirm the final menu baseline. Complete recipe yield, portion, equipment, nutrition, and source validation. Test representative meals through the Regional Kitchen and Finishing Kitchen process. |
| Implementation and site readiness | PHASE-01_RK_FK_Phase_Implementation_Master.xlsx PHASE-03_Finishing_Kitchen_Site_Readiness_Matrix.xlsx CONST-05_Operational_Readiness_Milestone_Plan.xlsx | Confirm the school sequence, current site conditions, and construction dependencies. Complete site assessments and close or document corrective actions. |
| Equipment and smallwares | EQUIP-01_Phase_1_Equipment_Master.xlsx EQUIP-04_Finishing_Kitchen_Equipment_Requirements.xlsx SMW-01_RK_FK_Smallwares_Master_Workbook.xlsx | Reconcile quantities with the current menu, phase plan, layouts, and utilities. Confirm school allocations, compatibility, units of measure, and replacement-stock assumptions. |
| Distribution and receiving | LOG-01_RK_FK_Distribution_Route_Plan.xlsx LOG-02_RK_Loading_Dispatch_Standard.docx LOG-03_FK_Receiving_Discrepancy_Procedure.docx | Validate routes, delivery windows, volumes, and run times. Confirm cold-chain controls, handoffs, receiving decisions, returnables, and disruption procedures through practical testing. |
| Food safety and traceability | SAFE-01_RK_FK_HACCP_Development_and_Control_Framework.xlsx SAFE-02_RK_FK_Food_Safety_Log_Set.xlsx SAFE-03_RK_FK_Traceability_Recall_Procedure.docx | Complete and approve the hazard analysis, control points, limits, record frequencies, and corrective actions. Validate traceability and recall procedures through an exercise. |
| Training and workforce readiness | TRN-01_RK_FK_Training_Requirements_Matrix.xlsx TRN-02_Training_Calendar_Provider_Implementation_Plan.xlsx | Confirm role requirements, prerequisites, providers, dates, sites, and dependencies. Define the completion and competency evidence needed for opening readiness. |
| Procedures, continuity, and opening readiness | SOP-01_RK_FK_SOP_Register.xlsx SOP-02_RK_FK_Opening_Readiness_Checklist.xlsx SOP-04_RK_FK_Core_Operational_SOP_Library.docx SOP-05_RK_FK_Emergency_Continuity_of_Operations_Procedures.docx TEST-01_RK_FK_Integrated_Pilot_Dry_Run_Plan.xlsx | Complete owner and approver review. Align procedures with accepted equipment, processes, and food-safety controls. Populate opening evidence and complete integrated dry runs and corrective actions. |